Annual Report

2013

Thabazimbi Municipality

June 2013 Annual report as required by section 127(2) of the MFMA. The report also incorporates service delivery performance report, audited financial statements; Auditor Generals’ report and the audit action plan thereon.

Thabazimbi Municipality

7 Rietbok Street

0147771525

0147771535

ANNUAL PERFORMANCE REPORT 2012/13

THABAZIMBI LOCAL MUNICIPALITY

TABLE OF CONTENTS

PREFACE…………………………………………………………….……

THABAZIMBI MUNICIPALITY PROFILE……………………………..

THABAZIMBI VISION AND MISSION…………………………………

KEY POLICY DEVELOPMENTS……………………………………….

CHAPTER 1

MAYOR’S FOREWORD ……………………………………..……...…….2

EXECUTIVE SUMMARY ………………………..………………….……2

MUNICIPAL MANAGER’S OVERVIEW……………………….…..…….5

CHAPTER 2

GOVERNANCE…………………………………………………….………7

CHAPTER 3

SERVICE DELIVERY PERFORMANCE REPORT………………………50

CHAPTER 4

FREE BASIC SERVICES AND INDIGENT SUPPORT………………..…69

CHAPTER 5

ORGANIZATIONAL DEVELOPMENT PERFORMANCE………….…...81

COMPONENT J

ORGANISATIONAL PERFOMANCE SCORECARD ……………….…..86

APPENDIX A; AUDITED FINANCIAL STATEMENTS

APPENDIX B; AG AUDIT REPORT

APPENDIX C; AUDIT ACTION PLAN

CHAPTER 1

1.1 MAYOR'S FOREWORD

a. Vision

To be the leading Municipality offering quality services in the most Economic, Affordable, Equitable and Sustainable manner.

b. Key Policy Developments

The successful 2011 Local Government Elections has brought hope once again not only to the people of Thabazimbi Local Municipality, equally to the ANC led government. The voter turnout increased from 36.58% to 48.36% in 2006 and 2011, respectively.  These elections have set a new impetus to the service delivery value chain and the approach of service delivery and communication of achievements and challenges. The new cadres of Council are a voice of the people and have been inducted to ensure that there is a systematic and cohesive way of not only planning, but also responding to service delivery challenges and effective and developmental communication.

The Draft 2013/14 Budget and IDP were prepared under challenging circumstances considering the number of issues that were raised during the Strategic Planning Session held on the 6 – 8 March 2013 in Northam Platinum Mine, as well as those raised by our communities during the stakeholder’s representative fora, public participation process and consultation during the month of October 2012.  It took a lot of effort and creativity to balance the Budget.  As we are all aware the world is still recovering from the economic meltdown.

We are talking to the mines to fund EPWP initiatives amongst others.

In conclusion, I would like to bring to your notice that the municipality boasts the following achievements;

- Successful launching of ward committees in all twelve wards

- A successful public participation to inform our IDP and Budget

- A very vibrant strategic planning session

- A high rank credible IDP in 2010/11,  2011/12 and 2012/13 respectively

The unique platform afforded to me as the Mayor of Thabazimbi Local Municipality has allowed me to promote the inclusivity, access and innovative thinking required to move the municipality towards a better future for all who work in it and those we would like to see join us. This is something I will continue to promote throughout the remainder of my term and beyond.

d. Public Participation

The mayoral Imbizo’s and the IDP forums are the main vehicles of the municipality which are used for public participation on which the communities will voice out their problems on which the councilors have to address them. The communities will tell the municipality which is their first priority

e. Future Actions

As municipality we have 12 priorities and 5 has been approved by the council. The 9 objectives that we have has to be reviewed annually

f. Agreements / Partnerships (announcements on special partnerships initiated)

The Thabazimbi Local Municipality is located in the south western part of Limpopo province and has Botswana as its international neighbor and two hour drive from Tshwane.The municipality has entered into partnership with Gaborone City Council, Anglo Platinum, Anglo-American, PPC, Northam Platinum limited, Trollope mining services and Marakele National Park

g. Conclusion

I wish to take this opportunity to thank fellow members of Council for the support and vision they have demonstrated during their term. We could not have come this far had it not been for their leadership and commitment to the service of residents.  Discipline, unity and focus even through trying times, are vital for the success of an institution.

I also wish to express our appreciation to the efforts made by management.  It was the guidance and advice from administration that kept us on the right track with regard to the decisions we made from time to time.

I also wish to thank the community, the various community structures such as the Ward Committees, for their understanding and patience. On our part, we did the best we could under the circumstances but they remain the judge on the extent to which we held their mandate. We thank the community in all eight wards, for the trust they put in us until the end of term.

Final thoughts on the year.

(Signed by:) ___________________________

P.A Mosito

1.2. MUNICIPAL MANAGER’S OVERVIEW

The development of Integrated Development Plan has been guided by the following Legislation, Protocols and Policies:

LEGISLATIVE FRAMEWORK (MUNICIPAL LEGISLATION)

- Demarcation Act 27/1998 – Municipal boundries

- Municipal Structures Act 117/1998 – Powers and Functions of municipalities

- Municipal Systems Act 32/2000 – Community Participation ( chapter 4), IDP (chapter 5) and Performance Management System (chapter 6)

- Municipal Finance Management Act 56/2003 – Multiyear Budgeting.

PROTOCOLS AND POLICIES

International Planning Context		:	UN Millenium Development Goals

Continental Planning Context		:	NEPAD & Regional Treaties

National Planning Context	:	State of the Nation Address (SONA), National Spatial Development Plan (NSDP), Medium Term                 Strategic  Framework (MTSF), Medium Term Budget Statement (MTBS), National Strategies, New Growth Plan,  12 National Outcome, particularly outcome 9 for municipalities, 5 National Manifesto Priorities.

Provincial Planning Context	:	State of the Province Address (SOPA), Limpopo Provincial Spatial Development Framework (LEGDP), Limpopo Provincial Spatial Development Framework (LPSDF), National Development Plan (NDP).

As the municipality we will strive to align our Strategic Plans (IDP) and Operational Plans (SDBIP/ Annual Performance) as per our constitutional mandate and powers and functions.  We are also creating a better life through provision of basic services and alleviating poverty in the short term and eventual eradication of poverty over the long period.

We are committed as the entire administration of Thabazimbi Municipality to give our undivided attention to the detail that would realize the proper implementation of the programme, support our political principals to achieve the promises they made during the local government elections as well as helping them to report back to their constituencies.

1.3. ORGANISATIONAL DEVELOPMENT OVERVIEW

ORGANISATIONAL DEVELOPMENT PERFORMANCE

Mayor

Executive committee

Municipal Manager

IDP manager

IDP steering committee				IDP representative forum

IDP project task team	Stakeholders structures		Ward committees		Public/communities

CHAPTER 2: GOVERNANCE

Thabazimbi Municipality is category B and it under the mayor. The council consist of 23 councillors of which the majority is of the ANC.The municipal manager is the accounting officer of the institution and played his role in terms of section 55 of the Municipal Systems Act The municipal manager has to advice the political structures and political office bearers of the municipality The IDP review was used as a tool for the community to participate in the affairs of the municipality The IDP forums were convened by the municipal manager  but chaired by the Mayor. The implementation of the performance management system also serves as a tool which is used by managers accountable for their performance. The municipal manager is the one who is assessing the section 57 managers and he is assessed by the mayor. The IDP forums is used to report the performance of councillors to the community

2.1 PUBLIC ACCOUNTABILITY AND PARTICIPATION

( COMPONENT C)

2.1.1 OVERVIEW OF PUBLIC ACCOUNTABILITY AND PARTICIPATION

Section 15(b) of the systems act requires a municipality to establish and organize its administration to facilitate and inculcate a culture of accountability amongst its staff. Section 16(i) states that a municipality must develop a system of municipal governance that compliments formal representative governance with a system of participatory governance. Section 18(i)(d) requires a municipality to supply its community with information concerning municipal governance, management and development

2.1.2 PUBLIC MEETINGS:

| DATE | KEY PERFORMANCE AREA |  |  |  | COMMENTS RAISED |  | PLAN WITH COMMITMENT DATE |  |  |  | RESPONSIBLE MANAGER |  |  |  |  | SIGN |  | DATE |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09-30 April 2013 | Basic Services and Infrastructure Development |  | Division |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Water and Sanitation |  | - 2009/10 Marakele water pipeline to Eco-Park not done.. |  | This will be addressed with the project: Development of a water master plan during 2014/15 financial year |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Water and sewer problem in ext.37 |  | August 2013 – The problem will be addressed with the project “ Thabazimbi upgrading of Pumpstation and pipeline Phase II” – 2013/14 Financial year |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Poor quality of drinking water |  | The problems will be addressed with the project “Thabazimbi Upgrading of Pumpstation and Pipeline Phase II” – 2013/14 Financial year |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Notice to be given to the community for water disconnection |  | Notices will be issued prior to disconnections |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Water meter not working in ext.3 and leakages in Regorogile 2 (Masepala). |  | Meter Audit – Leakage repairs ongoing (3 months) |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Water tanks not working at Smashblok. |  | Rhino Andulasite has committed to upgrade the boreholes during this year |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - 2011/12 budget for storm water pipes and sewer project in Rooiberg |  | Will be addressed by the project “Rooiberg upgrading of WWTW” – August 2013/14 |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - No mention is made of the completion of the Northam WWTW and the work in progress at the Thabazimbi WWTW since the drafting of the 2012/13 IDP document. |  | Northam Construction of a new 5Ml/d WWTW Outfall sewer - 98% complete (setting out, site clearance, Excavation, bedding cradle), pipe laying & Backfilling, Manhole installation). Pipe jacking (drilling and sleeve installation is completed. Rising main – 52% complete (setting out, site clearance, Excavation, bedding cradle), pipe laying & Backfilling). Pipe jacking (Site establishment is completed, Launch pit construction in progress. Thabazimbi upgrading of the WWTW: 3.5Ml/d – 6.5Ml/d Outfall sewer (setting out, site clearance, Excavation, bedding cradle), pipe laying & Backfilling) is 28% complete. Berm wall (setting out, site clearance, Excavation (soft material), Gabion structure (first block) is 40% complete |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The smell entering town impacts negatively on Tourists. |  | The smell will be eliminated on completion of the project: “Thabazimbi upgrading of the WWTW: 3.5Ml/d – 6.5Ml/d” which has already started and anticipated to the end of 2014 |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Irrigation system for farmers. |  | Matter to be referred to DWA |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Communal toilets to be closer to the community e.g. Rooiberg |  | VIP Toilets to be sourced during the 2013/14 financial year |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Blockage of toilets at hostel. |  | Unblocking and repair of toilets - June 2013 |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The open sewerage and water man holes on the Rustenburg road must get the lid and be properly closed. |  | The outfall sewer along the R510 is being upgraded and will be completed by August 2014 |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Water loss: If there is a pipe repair and the valves are closed for pressure, the water run into the storm water. Can this water be connected somewhere to the parks or garden? There is already a water shortage. |  | No leaks are permitted, leaks repaired on an ongoing process |  |  |  | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Electricity |  | - Timeframe on installation of electricity prepaid meters |  | July 2013 | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Street lights not working in Rooiberg and Hospital street. Some lights are on during the day and off at night in Northam, Smashblock, Masepala, Thabazimbi town. |  | Thabazimbi town: The eric switches were replaced with day night switches in the main roads. Busy attending to all the problems even over weekends | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Three highlights mast promised in Northam( Mojuteng) in the previous financial year. |  | R1,400,000 for installation of highmast lights budget for in the 2013/14 draft budget – July 2013 | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Notice to be given to the community for electricity disconnection. |  | Finance to respond | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Electricity needed at Skierlik and Apiesdoorn. |  | Await proclamation of land (the electrification plan of 2014/15) | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Solar System needed at Matikiring. |  | Meriting is electrified and can only be provided with solar geysers once formal structures erected | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - No transformers in new electricity boxes at ext. 5. |  | Transformer installed | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - It was stated that in 2013/14 the upgrade of electricity services was budgeted R3.2 million including upgrade of the substation, smart meter system and load management. It was not presented on the 9/04/13 meeting. |  | Upgrading of substation is in adjudication stage and will start in 2013/14 financial year. The conversion prepaid meters Is rolled over to next financial year. Load management system is rolled over to 2014/15 financial year | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Lampstand boxes which are binded by a blue wire. |  | Maintenance of street lights ongoing | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Roads and Storm water |  | - Pot holes on strategic roads e.g Steenbok street, corner 13th Avenue and Van der Bilj Street, Bosbok, Hibuscus etc. |  | - To appoint a service provider for supply and delivery of cold asphalt - To appoint a service provider for a period of 1 year for the repair of potholes - 01 July 2013 | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Speed humps needed at streets close to all schools, Rooiberg and Smashblock. Or if possible the erection of a 3 way stops street at T-junction of Michael and Deena Streets. |  | - Speed humps to be erected from wed(22 May) - To appoint a service provider for supply and delivery of road signs for a period of 1 year - 01 July 2013 | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Road upgrades to the amount of R2.3 milliom (at that stage comments were made that the amount is totally inadequate and the Honourable Mayor herself promised to come back to the residents with an answer but to date not. |  | - R4.6 m proposed for 13/14 budget for rehabilitation of roads | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The proposed paving for the extended Hamerkop Street beyond the railway bridge has been in the IDP for years now and nothing was done about it. |  | - R4.6 m proposed for 13/14 budget for rehabilitation of roads | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Maintenance and grading of gravel roads need to be included as strategic issues in all areas. |  | - To appoint a service provider for machinery and equipment - 01 July 2013 | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Paving at ext. 35 and 47 (cemetery side) previously budgeted. |  | - Ext 35 and 47 will be considered in the 2014/15 financial year | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Horrible pavement at Thabapark |  | - Ongoing maintenance - To start 27 May 2013 | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Incomplete projects e.g Northam |  | - Project to start as soon as Municipal manager approves the report submitted by Magago Engineering | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Contractors left some holes in some streets in Rooiberg |  | - To engage with the contractor to fix the road - To look at the outstanding amount and do it in-house | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The stormwateer pipe between Spar and Blinkblaar Street smells bad. |  | - Ongoing maintenance - To start 22 May | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Budget for Deena and Eland Streets is too high for maintenance (R5 and R4 millions). |  | - To source funding from private sectors - 01 July | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Rooikuil Street budget is too small (R1.2 mil) and during floods it causes problems. |  | - To source funding from private sectors - 01 July | Manager Technical Services, CG Booysen 082 333 4282. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Solid Waste and Refuse removal |  | - Occupants of Thabazimbi put refuse out next to the streets which causes ugly and messy situation. Municipality to provide refuse bins at strategic places in town. |  | Bins are already provided at strategic points and the Municipality is recently consistent in refuse removals due to having a 17m³ Compactor which was recently fitted with a new engine/ | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Some stop street signs are covered with leaves of nearby trees and are invisible for road users. |  | Trees are to be trimmed to lower levels effectively from Friday, 17 May 2013 | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Cutting of long grasses and tall trees at Regorogile ext.4, entrance near Lephalale road, Hamerkop and Jacaranda Streets. |  | A Committed Parks Team is working Seven Days a week to minimize backlog that they had due to lack of resources. Seven Brush Cutters purchased end of April 2013 and one Kudu Ride-on Machinery has been fixed which is also working non-stop | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Illegal dumping and poor refuse removal e.g. Thabazimbi town etc. |  | Illegal dumping is a problem anywhere in South Africa however education and awareness campaigns will be undertaken very often to minimize the problem. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Dumping site to be considered at Rooiberg |  | Land should be identified at Rooiberg for landfill development and rehabilitation of site that is currently used as a disposal facility be done by the end of July 2013.Possible negotiation with land owners for land donation. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Cemeteries to be fenced in Raphuti and graded. |  | Quotations to be sourced by the end of June 2013 | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Refuse tank needed at ext.5 |  | Don’t understand, not clear. If this is referring to bulk container, the bulk containers are not budgeted for this year, however this will be budgeted in 2014/2015 financial year. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Household refuse bins needed at Regorogile 2 (Masepala) and Dwaalboom. |  | Most of the household in Regorogile 2 have refuse bins and bulk containers have been provided at strategic areas in Regorogile 2 Dwalboom will be considered in the next financial year 2013/2014 and this will only be exercised if the municipality starts with the collection at the area. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Cleaning of sidewalks of main roads at Dwaalboom for primary school learners to be safe. |  | Sidewalks will be cleaned before 30 June 2013 as the concentration is still in Thabazimbi. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - R2.5 million will be frivolous expenditure. No reason exist to weigh waste been dumped. Clear guidelines can be made available on the approximate size of vehicles entering the site for payment. Weighing will not add value and will never provide a positive return on the investments. This action will be strongly objected if pursued. |  | Weigh bridges are requirements in terms of the legislations. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The bulk refuse bins which are on the corners of the streets became too much full when the truck is broken, because the people dump their domestic refuse in the bulk bins then they fly everywhere in the town. |  | Registration of contractors on the database for assisting in times of emergency is underway and this exercise is to be implemented in the next financial year. Mining houses around the Municipality also made commitments to purchase extra compactor trucks for the municipality. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Protection Services | - Speed Camera was repaired but not working again.. |  |  | Truvelo manufactures fixed the camera but their never installed as they did not bring laptop with DCAM. They have been contacted and they said their technicians will come on the 23rd May 2013. |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Procuring six patrol vehicles is the responsibility of SAPS not municipality. This cannot be supported. |  |  | Traffic patrol vehicles are needed for law enforcement and general patrol etc. We are not SAPS but Traffic Officers for TBZ Municipality and we are independent. |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - The recommended strategy would be to utilize the R2.5 million budgeted for the municipal chamber to build a licensing office. For this, the testing grounds in the industrial area can be utilized which safe cost on acquisition of property and is accessible and will provide ample space for parking. Phase 2 starting 2013/14 is the design and acquisition of property with 2014/15 construction commence. |  |  | We are awaiting Corporate Services Department and Technical Services Department to finalize the Kransburg issue. This is the latest information which is at advance stage. |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Advertisement Board/ Signage. This matter is older than the term of three consecutive Mayors, but still unresolved. The decision that Councillors will meet with Johan Barkenhuizen who had all the relevant documentation has still not happened. |  |  | The matter has been handed over to the Chief Operating Officer, Mr L J Motaung. |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Pick’n Pay T-junction need robot. |  |  | At the moment the Traffic Officers are doing point duty at the junction to control heavy traffic flow. Set of robots are needed in other junctions in TBZ and Northam and will be budgeted for in the 2014/2015 Financial year |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Operation of Traffic Officers needed regularly. |  |  | Over time arrangements need to be discussed and approved by the Municipal Manager |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - Stray animals and safe place for domestic animals Regorogile, Smashblock and Rooiberg. |  |  | Relevant sector department to be consulted regarding the matter by end of June 2013 |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - The municipality is using the stand behind the licensing office for dumping of refuse. |  |  | The Municipality is not dumping refuse behind the licensing office, but the bulk containers are placed at the open space to avoid illegal dumping, but community members are misusing the resources for its intended purposes. The containers will be removed as soon as the land is developed. |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | - The Traffic department should start working early at 04:00 am to give tickets to those who does not adhere to the law at Ben Alberts sharp curve and lines have to be painted. |  |  | Six qualified traffic officers dedicated to law enforcement need to be employed as urgent solution to the matter, in the starting of the new financial year 2013/2014 |  | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Disaster |  | - Family (Dora Mafora) still staying in disaster tent after their shack burned down on the 20 February 2013 at Regorogile. Awaiting corrugated irons from the municipality as promised. |  | The family was assisted with a tent and a wendy house, the Municipality does not erect shacks for members of community, Councillors must refrain from promising people that houses and shacks will be erected by Municipality | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Disaster plan to be on top of priority list |  | Not clear, however the plan should be developed or reviewed by the end of June 2013 | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Housing |  | - Housing backlog outdated. |  | - The true reflection of housing backlog statistics to be included in the IDP. The total housing backlog is 13862 which is inclusive of Low cost housing backlog at 8600, social housing at 5 262 and rental housing which is at 910. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - RDP houses and sites sold to Parkistanians e.g Raphuti, Regorogile, Northam etc. |  | Coghsta will be consulted to verify the status report of affected houses and the municipality will then take action together with Coghsta to evict those Pakistanians. These exercises will take a period of two months, which means it must be concluded end of June. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - RDP houses needed e.g Skierlik, Jabulane, Smashblock, Regorogile etc. |  | RDP houses cannot be built in some areas, feasibility studies are in progress to determine if areas are suitable for any developments.RDP houses will also be determined by CoGHSTA allocation. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Middle income houses and residential sites needed. |  | This is a joint project for the Community Services and Planning and Economic Development Departments. PED should identify land for building low-income houses and Community Services will identify the needs of the community | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Sports ,Art and Recreation |  | - Community Hall and Sports facility was on the previous budget in Northam but not done. |  | This project was not implemented due to budget constraints; however, it will be included in a proposal that is to be submitted to the Department of Environmental Affairs (National) for possible funding. Funding can be received in 2014/2015 financial year | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Clarity on payment of using municipal sports facilities by the community. |  | Clarity is provided during the week by the Senior Development Officer, and it will be published in the local Newspaper for those who are not able to go to the community Services Offices. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Renovation of all the municipal parks. |  | This project will form part of the proposal that will be submitted to the Department of Environmental Affairs. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Is there any possibility that a proper park for children be done. There is no place where the children can play. You can get someone to oversight the park and children pay R1.00 to get into for maintenance. |  | This project will form part of the proposal that will be submitted to the Department of Environmental Affairs. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Need for recreational facilities for adults. Now the people are driving to the town and we take our town income to other towns. |  | This project will form part of the proposal that will be submitted to the Department of Environmental Affairs. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The budget for sports is too high (R4 mil.) |  | This project will form part of the proposal that will be submitted to the Department of Environmental Affairs. | Manager Community Services, PG Rasesepa 078 293 4442 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATE | KEY PERFORMANCE AREA |  |  |  | COMMENTS RAISED |  | PLAN WITH COMMITMENT DATE | RESPONSIBLE MANAGER |  |  |  | SIGN |  |  | COMPLETION DATE |  |  |  |  |  |  |  |  |  |  |
| 9 – 30 April 2013 | Spatial Development |  | Division |  |  |  |  |  |  |  |  | Progress |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Town Planning |  | - Land for development (residence, business etc.) needed. |  | Acquisition of land for development. | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  | Proposals for purchasing land in Regorogile ext 11, Thbazimbi ext 48 and 38 submitted to funders. |  |  | March 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Matikiring issue to be speed up |  | Acquisition of land for relocations. | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  |  | June 2014 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Old municipal properties to be converted to residential/ accommodation |  | Conduct survey of available properties that can be converted to residential accommodation Submit report to MM s office. Commence with conversion . | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  |  | Dec 2013 |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Old clinic in Regorogile to be converted to Youth Centre. |  | Submit a report to MM s office on the possibility of conversion. | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  |  | June 2013 |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Building Control |  | - Businesses in residential sites (Parkistanian Spazas) |  | SAPS regulates the spazas and other businesses in the residential area. | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |
| DATE | KEY PERFORMANCE AREA |  |  |  | COMMENTS RAISED |  | PLAN WITH COMMITMENT DATE | RESPONSIBLE MANAGER |  |  |  | SIGN |  | DATE |  |  |  |  |  |  |  |  |  |  |  |
|  | Local Economic Development |  | LED |  | - Unemployment especially the Youth. |  | Employment strategy is implemented by the political office. | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  | Ongoing |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Clarity on PPC recruitement. |  | Employment strategy is implemented by the political office. | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  | Ongoinga |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Regulation of Hawkers at Warmbad Weg and other strategic places in town. |  | Regulate the hawkers through SAPS | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - SMME training |  | Trainings are ongoing. | Manager Planning and Economic Development, MS Mabitsela 082 552 2465 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATE | KEY PERFORMANCE AREA |  |  |  | COMMENTS RAISED |  | PLAN WITH COMMITMENT DATE |  | RESPONSIBLE MANAGER |  |  |  | SIGN |  |  |  | DATE |  |  |  |  |  |  |  |  |
| 9 – 30 April 2013 | Financial Viability |  | Division |  | - High and inaccurate water bills |  | We are in the process of identifying and replacing all faulty and meters that are not working. All faulty meters will be replaced by the 30 June 2013. The meter reading service provider has been engaged to ensure that meters are read and reports will be submitted to the CFO’s office on a monthly basis for monitoring. Exception reports for very high and low monthly consumptions will be reviewed and signed off before billings are made starting from 01 June 2013. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Water bills with incorrect personal details in Northam |  | We are currently busy with an operation for data cleansing and verification. (Operation Ithlagise). The billing system will be updated with the data collected and verified by 30 June 2013. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Stakeholders appreciated the finance department for giving the community feedback report on the discussion of Section 71 report. |  | Thank you. We will continue ensuring that monthly reports are done and made public as required by the MFMA. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Water readings not regularly taken. |  | Monthly reports from the service provider doing metering services will be received and reviewed on time before billings are finalized. Exception reports for very high and low monthly consumptions will be reviewed, corrective actions taken and signed off before billings are made starting from 01 June 2013. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Proof of payments for services used by contractors and EMS stationed in municipal premises at Northam. |  | No billings were done for these tenants. Corporate services will be engaged so that a list of municipal properties rented out is submitted to finance for billing purposes with copies of rental agreements. Billings will be done from 01 July 2013. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - I received the notice of valuation of my property on the 5 April 2013 and was given until the 12 April 2013 to give notice of objection. My question to Municipal Manager is to how long period of notice for objection should lawfully be given, could not be answered. The valuation roll was not available on the internet on time. |  | In terms of Section 59(a) of the MPRA the valuation roll must be published twice in the media and in the gazette for thirty days for inspection by the public. The municipalities have published the valuation roll as required during the week ending 1st March and 08 March 2013 in the media and have placed the valuation roll on the website for thirty days. The municipality has complied with the MPRA with regard to notifying the consumers. The notices sent was an additional resource used by the municipality to inform the ratepayers. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The 2012/13 actual expenditure is not listed on the current Draft. |  | The actual expenditure for 2011/12 as audited is shown on the budget as well as the expenditure forecast for 2012/13 as per treasury guideline. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The Rates Policy never went through a renewal process. |  | The draft rates policy has been reviewed and published on the website for public inspection. A meeting was held with the Thabazimbi taxpayer association and the draft rates policy was discussed. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The increase of revenue on Rates is incorrect – the farms JQ is not on the Valuation roll. The increase comes out of the increase on the valuation increase and not as indicated as previously non payers. |  | As legislated all objections in writing were invited from rates payers and response in writing will also be provided by the 17th of May 2013. The property rates tariffs has been reduced by 19% for all residential and agricultural properties. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The budget for maintenance is not suitable to maintain a healthy environment |  | An amount of R 22.3million has been budgeted for repairs and maintenance which is 10% of the total operating expenditure as per treasury guidelines. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Complain of electricity on account number: 68312/LOURENS, Steenbok No.21 is R31 210.72 by Bosveld Eiendomme Thabazimbi. |  | We have checked the account and the amount outstanding is R 1045.49 for property rates. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Complain of double billing on account number: 060782/0231713, Bosveld Park no.7 by Bosveld Eiendomme Thabazimbi. |  | We have checked the account and the amount outstanding is R2366.08. We investigated the account and no double billing was identified. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The municipality has an office with staff dealing with the registration of indigents. This office must on annual bases provide input on the number of indigents which has been registered for free service. |  | At the moment the municipality has 223 registered indigents. A public notice will be made by the 05th June 2013 on the media to remind customers to register as indigent for the 2013/14 financial year. |  | Chief Financial Officer, LC Malema 074 727 1918 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATE | KEY PERFORMANCE AREA |  |  |  | COMMENTS RAISED |  | PLAN WITH COMMITMENT DATE | RESPONSIBLE MANAGER |  |  |  | SIGN |  | DATE |  |  |  |  |  |  |  |  |  |  |  |
| 9 – 30 April 2013 | Municipal Transformation and Organisational Development |  | Division |  | - Street Trading by-law to be revisited as there was never community consultation at Northam. |  | Public Participation was done. All By-laws were deposited at all satellite stations. To prove that this was done , we have comments from Mr Enly from Toyota Satelite Stations | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Lack of monitoring and supervision of employees during working hours. |  | Each Manager Should manage his or her employees. If we hope to succeed in this. | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Learnerships needed by the community. |  | It is in progress | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Clarity on eviction letter of Raphuti residents by the municipality. |  | The team handling this has since advised that we should wait until they are through with the Housing Consumer Education. | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Regulation of noise by neighbours during funerals. |  | All we need to do is to enforce the by-law regarding nuisance. | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Employment equity: much is said of the employment of Coloured and Indians. To ensure transparency, the total equity plan must be opened up, which include the number of white people employed. Looking from outside, it appears that white people has been marginalized. This information must be tabled. |  | In as far as this concerned , yes it is true we are not complying but we hope will be able to address this in the new financial year. | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Problem at the main office of the municipality where disability people are unable to get in the office. The steps to the 1st floor are a problem for the old people. |  | Purchase of Kransberg will address this. | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - To spend R2.0 million on the building to upgrade it, it is irresponsible. With this expenditure a total amount of R4.5 million is wasted. With this money we can go a long way of building a purpose designed building, catering for future needs. Spending this money must be stopped at all cost. |  | This is intended for renovation. | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Clarity on why the Municipal Manager’s salary is more than the Potchefstroom Municipal Manager. |  | The MM’s salary is negotiated between the Mayor and Municipal Manager himself. | Manager Corporate Services, RJ Mogale 082 796 4855 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATE |  | KEY PERFORMANCE AREA |  |  | COMMENTS RAISED |  | PLAN WITH COMMITMENT DATE | RESPONSIBLE MANAGER |  |  |  | SIGN |  | DATE |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Good Governance and Public Participation | Division |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Public Participation |  | - Councillors not holding meetings in their Wards |  | The ward committees are trained to understand their responsibilities better, they are able to assist Ward Councilors with the affairs of the ward. The Public Participation and Coordinator have been appointed to work with ward committees. | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Ward Committees not submitting ward needs to the office of the Speaker. |  | The ward committees are given the short training on IDP which assisted them to understand that the ward profiling is very impotant in development of the community. | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Ward Commitees practicing favouritism in Ward 4 (Raphuti) |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - Councillors to visit all the areas in their wards especially farm areas. |  | The Public Participation Officer with Ward committees are able to assist Ward Councilors with ward profiling and reports currently | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The benefit of Community Development Forum and the restarting of EPWP job at Jabulani. |  | This matter have to be solved by involving relevant role players and taking the issue of budget into consideration | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The same old promises were made to the people of the ward referred to as “the 20% paying for the 80%”. The residents from these wards had enough of the promises and request clear action on the matters raised time and time again. |  | The matter of payment of services has received serious attention and the Revenue collection Strategy is in place for implementation. | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Communication |  | - Late starting of all meetings organized by the municipality Punctuality). |  | The participation of the community in the IDP Public Participation processes is very important. We therefore apologize for starting the meetings late although we sometimes do it for allowing our community to be in attendance and give inputs which will bring developments | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The venue for public participation of the 9 April 2013 was too small and not conducive as people outside could not hear the Mayor. |  | The selection of the venue was informed by previous attendance record. We will be giving it a serious attention | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | - The Draft IDP and Budget was only available on the municipal website a few hours prior to the meeting. |  | The matter has received serious attention in 2013/14 budget for the upgrading our IT system. | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | PMS |  | - Past performance figures to reflect in the Budget and IDP on what has been achieved in the previous year. |  | The matter of budget performance and municipal Performance is legislated it will be handled in accordance with legislation | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | IDP |  | - Outdated statistics (figures). |  | The updated figures will be factored in the final IDP document for 2013/14 before the end of May 2013 | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 – 30 April 2013 |  |  | Social Service (Sector departments) |  |  | COMMENTS RAISED | PLAN WITH COMMITMENT DATE |  |  | RESPONSIBLE MANAGER |  | SIGN |  | DATE |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Dept. of Home Affairs. |  |  | - Community standing long queues for acquiring identity documents. Request assistance from the municipality in this regard. | The Sector Dept responsible will be engaged .The statistics relating to service needs will be given attention and factored in our IDP Analysis phase for 2014/15. |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Dept. of Labour |  |  | - Unfair dismissal of workers at Skierlik | The matter will be investigated and whoever that is unfairly dismissed has the legal rights to take the matter to Dept of Labor |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Dept. of Education |  |  | - Classrooms in Apiesdoorn to be converted to a crèche. | The property belongs to Thabazimbi Local Municipality, therefore it has the legal rights to handle it according to their legal mandate. |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - Establishment of an FET college in Thabazimbi. | This is the good idea for community development and the relevant role players will play part in the planning of it |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - Overcrowding of classrooms (85 learners in one room) and there is no water and toilets are not working at Smashblock. | The Provincial Public works are actually responsible for maintenance of Public schools and SGB of the school must play major role in this matter.IDP office will approach Education Dept for correcting the situation in 2013/14 financial year or subsequent financial years |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - There are no crèches at Wards 6 & 7. | Correct ward profiling will assist IDP office to communicate the community needs to relevant role players |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Dept. of health |  |  | - Bad treatment of patients by Nurses at the clinics especially Dwaalboom. | The matter will be reported to relevant Department for further investigations |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - Ambulance Services to be closer to the community and not wait for the ambulance from Modimolle in an emergency situation. | Thabazimbi and Northam towns are provided with Ambulance and Medical Emergency Services however the gaps will be reported to relevant Dept. |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Dept. of Rural Development and Land Reform |  |  | - Eviction and bad treatment of farm residents by owners at Heuningvlei. | The matter will be investigated and reported to relevant Depts. The victims must also report ill-treatment to the SAPS and Dept of labor. |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | SAPS |  |  | - SAPS Officials harasses residents at Rooiberg and Raphuti. | The matter of Policing the communities must be done with dignity and respect it deserve and anything contrary to that, it is either criminal or offensive, therefore it must be reported to the relevant office or unit |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - Small business and tavern owners are paying R500 to the Police Officers and they said is a joint venture with the municipality. Clarity as to where the money is taken. | The Police have the mandate to issue fines or arrest whoever that breaches the law, however the municipality has the legal mandate to collect revenue in their jurisdiction and it is handled as regulated by financial policies and MFMA. |  |  | Chief Operations Officer, LJ Motaung 083 766 2605 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

2.1.3 COUNCILLORS

.Our Municipality has 23 Councillors and twelve wards. We have the schedule of the meetings which is followed. There are some portfolio committees namely financial and transformation council committee, community service council and the infrastructure, planning and Economic Development council committee

|  | COUNCILORS | DESIGNATION | WARD |  |
| --- | --- | --- | --- | --- |
| 1. | CLLR KELEBONE RAGEL MOKWENA | WARD COUNCILOR | WARD 1 |  |
| 2. | CLLR PAUL ANTHONY SCRUTON | WARD COUNCILOR | WARD 2 |  |
| 3. | CLLR STEPHEN GABAETSIWI LERUMO | WARD COUNCILOR | WARD 3 |  |
| 4. | CLLR THEMBA MKANSI | WARD COUNCILOR | WARD 4 |  |
| 5. | CLLR SEBAKISHE ISAAC MANALA | WARD COUNCILOR | WARD 5 |  |
| 6. | CLLR MAVHU LYDIA SIKHWARI | WARD COUNCILOR | WARD 6 |  |
| 7. | CLLR TWO DAYS MOLEFE | WARD COUNCILOR | WARD 7 |  |
| 8. | CLLR CATHERINE SEMAKALENG SIKWANE | WARD COUNCILOR | WARD 8 |  |
| 9. | CLLR DIALE AARON MOATSHE | WARD COUNCILOR | WARD 9 |  |
| 10. | CLLR JOHN MICHAEL FISHER | WARD COUNCILOR | WARD 10 |  |
| 11. | CLLR SYLVIA GAONYADIWE MATSIETSA | WARD COUNCILOR | WARD 11 |  |
| 12. | CLLR MARY DIKELEDI TLHABADIRA | WARD COUNCILOR | WARD 12 |  |
| 13. | CLLR BEAUTY NOKUZOLA MAGUGA | PR COUNCILOR |  | WARD |
| 14. | CLLR ADOLPH STEPHEN KHUMALO | PR COUNCILOR |  | WARD |
| 15. | CLLR MIDAH MOSELANE | PR COUNCILOR |  | WARD |
| 16. | CLLR MOIFADI ESTHER SEMADI | PR COUNCILOR |  | WARD |
| 17. | CLLR PATRICIA ALETTAH MOSITO | PR COUNCILOR |  | WARD |
| 18. | CLLR RAMEHLARE ADOLF RAMOGALE | PR COUNCILOR |  | WARD |
| 19. | CLLR DERICK RODNEY DANIELS | PR COUNCILOR |  | WARD |
| 20. | CLLR LAMBERT HENDRIK JOUBERT | PR COUNCILOR |  | WARD |
| 21. | CLLR FRANCO LOOTS | PR COUNCILOR |  | WARD |
| 22. | CLLR PIET STRYDOM | PR COUNCILOR |  | WARD |
| 23. | CLLR RUDOLF CORNELIUS DU PREEZE | PR COUNCILOR |  | WARD |

COMMENT ON THE EFFECTIVENESS OF THE PUBLIC MEETINGS HELD:

The meetings were effective in that members of public, councillors and municipal officials were able to get first hand information from key decision makers to ask questions directly and to raise their problems regarding services delivery by all spheres of government and get response immediately.

2.1.4 IDP PARTICIPATION AND ALIGNMENT

| IDP Participation and Alignment Criteria* | Yes/No |
| --- | --- |
| Does the municipality have impact, outcome, input, output indicators? | Yes |
| Does the IDP have priorities, objectives, KPIs, development strategies? | Yes |
| Does the IDP have multi-year targets? | Yes |
| Are the above aligned and can they calculate into a score? | Yes |
| Does the budget align directly to the KPIs in the strategic plan? | Yes |
| Do the IDP KPIs align to the Section 57 Managers | Yes |
| Do the IDP KPIs lead to functional area KPIs as per the SDBIP? | Yes |
| Do the IDP KPIs align with the provincial KPIs on the 12 Outcomes | Yes |
| Were the indicators communicated to the public? | Yes |
| Were the four quarter aligned reports submitted within stipulated time frames? | Yes |

2.2 CORPORATE GOVERNANCE( COMPONENT D)

.TLM always is determined to adhere to principles of good governance at all times. These include aspects of managing risk measures aimed at addressing fraud and anti-corruption and to protect whistle-blowers, open, credible and transparent SCM processes. Adherence to the rule of law, providing information to the public and other stakeholders and providing good quality and reliable services

2.2.1 OVERVIEW OF CORPORATE GOVERNANCE

The communication strategy is in place in TLM. The challenge for it is that only one person is appointed on it. i.e communication officer. The municipal information technology as well as the website needs to be upgraded. The risk management policy which is in place minimise negative outcomes and optimizing opportunities

2.2.2  RISK MANAGEMENT

The accounting officer of a municipality must ensure that that the municipality has and maintains effective, efficient and transparent systems of financial and risk management and internal control.

Services Department roles

- Treasury Department

- CogHSTA Departments

The major roles of aforementioned

- prescribe uniform norms and standards

- monitor and assess the implementation of the  and MFMA

- Assist Institutions in building their capacity for efficient, effective and transparent financial management.

- Enforce the MFMA.

- Advise

2.2.3 FRAUD AND ANTI-CORRUPTION STRATEGY

Fraud is defined as unlawful and intentional making of a misrepresentation which causes actual prejudice or which is potentially prejudicial to another.  The attempted fraud is treated as seriously as accomplished fraud.  The term is used to describe such acts as deception, bribery, forgery, extortion, corruption, theft, conspiracy, embezzlement, misappropriation, false representation, concealment of material facts, collusion etc.

Corruption in terms of section 3 of the prevention and Combating of Corrupt Activities Act, is committed by any person who directly or indirectly.

Accepts or agrees or offers to accept any gratification from any other person, whether for the benefits of himself or herself or for the benefit of another person: or

gives or agrees or offers to give to any other person any gratification, whether for the benefit of that other person or for the benefit of another person, in order to act, personally or by influencing another person so to act, in a manner that amounts to the :

illegal, dishonest, unauthorized, incomplete, or biased; or misuse or selling of information or material acquired in the course of the, exercise, carrying out or performance of any powers, duties or functions arising out of a constitutional, statutory, contractual or any other legal obligation, that amounts to-

- the abuse of a position of authority;

- a breach of a position of authority;

- the violation of a legal duty or a set of rules;

Key risk areas

- Procurement processes

- Assets management

- Revenue collection

- Appointment processes

2.2.4 SUPPLY CHAIN MANAGEMENT

OVERVIEW SUPPLY CHAIN MANAGEMENT

The Supply Chain Management (SCM) Policy of the Thabazimbi Local Municipality sets a framework for meaningfully managing, monitoring and reporting of procurement activities and provides the procedures to be followed in procurement. The SCM policy is located within the South African legislative framework. The laws that are currently applicable include: the Constitution of the Republic of South Africa (Act 108 of 1996), the Preferential Procurement Policy Framework Act (Act 5 of 2000) and the Local Government: Municipal Systems Act (Act 32 of 2000), Local Government: Municipal Finance Management Act (Act 56 of 2003) and the Broad Based Black Economic Empowerment Act (Act 53 of 2003). The principles of this policy are those set out in the legislative frameworks mentioned above in particular that of realizing value for money and good governance and ensuring cost effectiveness and competitive equitable, transparent and fair access to procurement opportunities to all. The SCM policy forms part of the overall business systems of the TLM and will be supported by specific procurement systems aimed at improving both procurement and overall business performance.

| 2.2.5 BY-LAWS |  |  |  |  |
| --- | --- | --- | --- | --- |
| By-laws Introduced during 2012/13 |  |  |  |  |
| Newly Developed | Date Revised | Public Participation Conducted Prior to Adoption of By-Laws (Yes/No) | Dates of Public Participation | Date of Publication |
| N/A | N/A | N/A | N/A | N/A |
| N/A | N/A | N/A | N/A | N/A |
| N/A | N/A | N/A | N/A | N/A |
| N/A | N/A | N/A | N/A | N/A |
| N/A | N/A | N/A | N/A | N/A |
| N/A | N/A | N/A | N/A | N/A |
| N/A | N/A | N/A | N/A | N/A |
| N/A | N/A | N/A | N/A | N/A |

CHAPTER 3 - SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT)

INTRODUCTION

The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA).  In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”

As the budget gives effect to the strategic priorities of the municipality it is important to supplement the budget and the IDP with a management and implementation plan.  The SDBIP serves as the commitment by the Municipality, which includes the administration, council and community, whereby the intended objectives and projected achievements are expressed in order to ensure that desired outcomes over the long term are achieved and these are implemented by the administration over the next twelve months.

The SDBIP provides the basis for measuring performance in service delivery against quarterly targets and implementing the budget based on monthly projections.  Circular 13 further suggests that “the SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community.”

The purpose of the SDBIP is to monitor the execution of the budget, performance of senior management and achievement of the strategic objectives set by Council. It enables the municipal manager to monitor the performance of senior managers, the mayor to monitor the performance of the municipal manager, and for the community to monitor the performance of the municipality. In the interests of good governance and better accountability, the SDBIP should therefore determine and be aligned with the performance agreements of the municipal manager and senior managers.

The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is required by the Municipal Finance Management Act (MFMA). In terms of Circular 13 of National Treasury, “the SDBIP gives effect to the Integrated Development Plan (IDP) and budget of the municipality and will be possible if the IDP and budget are fully aligned with each other, as required by the MFMA.”

COMPONENT A: BASIC SERVICES

Thabazimbi Local Municipality is one of the Municipalities in the province that is rendering basic services to the community such as water, waste water , electricity, waste management. Even the indigents are taking care of because they receive free electricity, sanitation and waste removal

INTRODUCTION TO BASIC SERVICES

To ensure that relevant skilled employees are appointed and trained in Service Delivery Departments, specifically Technical Services the following interventions were done:

- Road Maintenance

- Storm Water maintenance

- Refuse and Hygiene Management

- Plumbing and Electrical  Training

3.1 WATER PROVISION

Thabazimbi, Regorogile and Northam currently have a quota of 9 mega liters per day from Magalies board.Regorogile and Thabazimbi have additional supply from seven boreholes. The boreholes are located at Group 5,12 and Kumba Iron Ore Mine.Rooiberg and Raphuti currently source their water from local boreholes Schilpadnest water is supplied from three working boreholes without chlorination facilities.

| Water Service Delivery Levels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Households |  |  |  |  |  |  |
| Description |  |  |  |  | 2010/11 |  | 2011/12 |  | 2012/13 |  |  |  |  |  |  |
|  |  |  |  |  | Actual |  | Actual |  | Actual |  | Actual |  |  |  |  |
|  |  |  |  |  | No. |  | No. |  | No. |  | No. |  |  |  |  |
| Water: (above min level) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Piped water inside dwelling |  |  |  |  | 24405 |  | 10624 |  | 10624 |  | 10624 |  |  |  |  |
| Piped water inside yard (but not in dwelling) |  |  |  |  | 24405 |  | 6281 |  | 6281 |  | 6281 |  |  |  |  |
| Using public tap (stand pipes ) |  |  |  |  | 2040 |  | 5064 |  | 5064 |  | 5064 |  |  |  |  |
| Other water supply (within 200m) |  |  |  |  | 1037 |  | 1037 |  | 1037 |  | 1037 |  |  |  |  |
| Minimum Service Level and Above sub-total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Minimum Service Level and Above Percentage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Water: (below min level) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Using public tap (more than 200m from dwelling) |  |  |  |  | 1037 |  | 1037 |  | 1037 |  | 1037 |  |  |  |  |
| Other water supply (more than 200m from dwelling |  |  |  |  | 1037 |  | 1037 |  | 1037 |  | 1037 |  |  |  |  |
| No water supply |  |  |  |  | N/A |  | N/A |  | N/A |  | N/A |  |  |  |  |
| Below Minimum Service Level sub-total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Below Minimum Service Level Percentage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total number of households* |  |  |  |  | 23871 |  | 23871 |  | 23872 |  |  |  |  |  |  |
| * - To include informal settlements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Households - Water Service Delivery Levels below the minimum |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Households |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description |  | 2010/11 |  |  |  | 2011/12 |  | 2012/13 |  |  |  |  |  |  |  |
|  |  | Actual No. |  |  |  | Actual |  | Original Budget |  | Adjusted Budget |  |  | Actual |  |  |
|  |  |  |  |  |  | No. |  | No. |  | No. |  |  | No. |  |  |
| Formal Settlements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total households |  | 23871 23871 |  |  |  | 23872 |  | 23.872 |  | 23.872 |  |  | 0 |  |  |
| Households below minimum service level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proportion of households below minimum service level |  |  |  |  |  | 23872 |  | 23872 |  | 23872 |  |  | 0 |  |  |
| Informal Settlements |  | 8 |  |  |  | 8 |  | 8 |  | 8 |  |  |  |  |  |
| Total households |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Households ts below minimum service level |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proportion of households ts below minimum service level |  | 23871 |  |  |  | 23872 |  | 23872 |  | 23872 |  |  | 0 |  |  |
| Access To Water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Access to Water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Proportion of households with access to water points* |  | Proportion of households with access to piped water |  |  |  |  | Proportion of households receiving 6 kl Free Basic Water# |  |  |  |  |  |  |  |
| 2010/11 | 11393 |  | 11393 |  |  |  |  | 1543 |  |  |  |  |  |  |  |
| 2011/12 | 23871 |  | 23871 |  |  |  |  | 123871 |  |  |  |  |  |  |  |
| 2012/13 | 23871 |  | 23871 |  |  |  |  | 123871 |  |  |  |  |  |  |  |

| Water Service Policy Objectives Taken From IDP |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Service Objectives | Outline Service Targhets | 2010/11 |  | 2011/12 |  | 2012/13 |  |
|  |  | Target | Actual | Target | Actual | Target | Actual |
| Service Indicators |  |  |  |  |  |  |  |
| (i) | (ii) |  |  |  |  |  |  |
| Service Objective To coordinate and monitor infrastructure development for provision of access to basic services |  |  |  |  |  |  |  |
| Households without minimum water supply | Additional Households provided with minimum water supply during the year (Number of households (HHs) without supply at year end) | 1609 | 660 | 949 | 715 | 364 | 233 |
| Improve reliability of water supply | Reduce the number of interruptions (Ints) in supply of one hour or more compared to the baseline of 2010/11(xxx interruptions of one hour or more during the yr) | 10 | 13 | 7 | 9 | 7 | 3 |
| Improve water conservation | Reduce unaccountable water levels compared to the baseline of 2010/11 (xxx kilolitres (KLs) unaccounted for during the yr) | 20%of 12 Ml/d | 48% of 12M/d | 20% of 12 Ml/d | 45% of 12 Ml/d | 20% of 12 Ml/d | 45% of 12 Ml/d |

| Employees: Water Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 2 | 2 | 0 | 0% |
| 4 - 6 | 9 | 9 | 9 | 0 | 0% |
| 7 - 9 | 1 | 1 | 1 | 0 | 0% |
| 10 - 12 | 2 | 2 | 2 | 0 | 0% |
| 13 - 15 | 13 | 13 | 13 | 0 | 0% |
| Total | 27 | 27 | 27 | 0 |  |
| Financial Performance 2012/13: Water Services |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 61 789 000 | 51 171 000 | 51 171 000 | 51 171 000 |  |
| Expenditure: |  |  |  |  |  |
| Employees | 2 934 883.81 | 3 037 906.90 | 3 855 404.03 | 3 855 404.03 |  |
| Repairs and Maintenance | 2 843 000 | 4 369 000 | 4 369 000 | 4 369 000 |  |
| Other | 22 055 116.19 | 25 137 093.10 | 24 319 595.97 | 24 319 595.97 |  |
| Total Operational Expenditure | 27 833 000 | 32 544 000 | 32 544 000 | 32 544 000 |  |
| Net Operational (Service) Expenditure | 27 833 000 | 32 544 000 | 32 544 000 | 32 544 000 |  |
| Capital Expenditure 2012/13 Water Services |  |  |  |  |  |
| Capital Projects | 2012/13 |  |  |  |  |
|  | Budget | Adjustment Budget | Actual Expenditure | Variance from original budget | Total Project Value |
| Total All | 2 811 000 | 2 811 000 | 2 811 000 |  |  |

3.2    WASTE WATER (SANITATION) PROVISION

INTRODUCTION TO SANITATION PROVISION

The sewer network in Regorogile,Thabazimbi,Ipelegeng and Mmebane needs upgrading.The municipality will upgrade the sewer lines and the Thabazimbi waste water treatment works to double the treatment capacity.This will accommodate the low cost houses tthat municipality intends building in the next few years.The municipality is investing MIG funds in this project.We also anticipate huge SMM’S development and creation of 100 job opportunities

| Sanitation Service Delivery Levels |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| *Households |  |  |  |  |  |  |
| Description | 2010/11 | 2011/12 | 2012/13 | 2012/13 |  |  |
|  | Outcome | Outcome | Outcome | Target | Actual |  |
|  | No. | No. | No. | No. | No. |  |
| Sanitation/sewerage: (above minimum level) |  |  |  |  |  |  |
| Flush toilet (connected to sewerage) | 24405 | 16646 | 16646 | 16646 | 0 |  |
| Flush toilet (with septic tank) | 870 | 99 | 99 | 99 | 0 |  |
| Chemical toilet | 189 | 189 | 44 | 44 | 0 |  |
| Pit toilet (ventilated) | 1164 | 5075 | 135 | 135 | 0 |  |
| Minimum Service Level and Above sub-total | 15455 | 15455 | 15455 | 15455 | 0 |  |
| Minimum Service Level and Above Percentage |  |  |  |  |  |  |
| Sanitation/sewerage: (below minimum level) |  |  |  |  |  |  |
| Other toilet provisions (below min.service level) | N/A | N/A | N/A | N/A | N/A |  |
| Below Minimum Service Level sub-total | N/A | N/A | N/A | N/A | N/A | N/A |
| Below Minimum Service Level Percentage | N/A | N/A | N/A | N/A | N/A | N/A |
| Total households |  |  |  |  |  |  |
| *Total number of households including informal settlements |  |  |  |  |  |  |
| Households - Sanitation Service Delivery Levels below the minimum |  |  |  |  |  |  |
| Households |  |  |  |  |  |  |
| Description | 2010/11 |  | 2011/12 | 2012/13 |  |  |
|  | Actual |  | Actual | Original Budget | Adjusted Budget | Actual |
|  | No |  | No. | No. | No. | No. |
| Formal Settlements |  |  |  |  |  |  |
| Total households | 23871 |  | 2141.63 | 2141.63 |  |  |
| Households below minimum service level | N/A |  | N/A | N/A | N/A | N/A |
| Proportion of households below minimum service level | N/A |  | N/A | N/A | N/A | N/A |
| Informal Settlements | 8 |  | 8 |  |  |  |
| Total households |  |  |  |  |  |  |
| Households below minimum service level | 23871 |  | 23871 | 2141.63 |  |  |
| Proportion of households below minimum service level | N/A |  | N/A | N/A | N/A | N/A |

| Access To Sanitation |  |  |  |
| --- | --- | --- | --- |
| Access to Sanitation |  |  |  |
|  | Proportion of households receiving sanitation |  |  |
| 2010/11 | 20270 |  |  |
| 2011/12 | 36 576 |  |  |
| 2012/13 | 81 293 |  |  |

| Employees: Sanitation Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 2 | 2 | 0 | 0% |
| 4 - 6 | 9 | 9 | 9 | 0 | 0% |
| 7 - 9 | 1 | 1 | 1 | 0 | 0% |
| 10 - 12 | 2 | 2 | 2 | 0 | 0% |
| 13 - 15 | 13 | 13 | 13 | 0 | 0% |
| Total | 27 | 27 | 27 | 0 | 0% |
| Financial Performance 2012/13: Sanitation Services |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 12 323 106.63 | 10 182 000.00 | 12 154 000.00 | 12 154 000.00 |  |
| Expenditure: |  |  |  |  |  |
| Employees | 1 939 394.54 | 2 679 444.03 | 1 322 933.31 | 1 939 394.54 |  |
| Repairs and Maintenance | 3 673 000 | 3 673 000 | 3 673 000 |  |  |
| Other |  |  |  |  |  |
| Total Operational Expenditure | 5 580 290.98 | 5 657 000.00 | 7 366 183.32 | 7 366 183.32 |  |
| Net Operational (Service) Expenditure | 5 580 290.98 | 5 657 000.00 | 7 366 183.32 | 7 366 183.32 |  |
| Capital Expenditure 2012/13: Sanitation Services |  |  |  |  |  |
| Capital Projects | 2012/13 |  |  |  |  |
|  | Budget | Adjustment Budget | Actual Expenditure | Variance from original budget | Total Project Value |
| Total All | 51 792 000 | 46 433 000 | 46 433 000 |  |  |

| Service Objectives | Outline Service Targets | 2010/11 |  |  |  | 2011/12 |  |  | 2012/13 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Target |  | Actual |  | Target | Actual |  | Target |  | Actual |  |
| Service Indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| (i) | (ii) |  |  |  |  |  |  |  |  |  |  |  |
| Service Objective To coordinate and monitor infrastructure development for provision of access to basic services |  |  |  |  |  |  |  |  |  |  |  |  |
| eg Provision of toilets within standard | Additional Households (HHs) provided with minimum sanitation during the year (Number of HHs remaining without minimum sanitation at year end) | 954 | 529 |  | 425 |  |  | 425 |  | 960 |  | 960 |

WASTE MANAGEMENT (THIS SECTION TO INCLUDE: REFUSE COLLECTIONS, WASTE DISPOSAL

INTRODUCTION TO WASTE MANAGEMENT

Waste Management service delivery including refuse storage, refuse removal, refuse dumps and solid waste disposal, is a local government function in terms of Schedule 5 of the Constitution of the Republic of South Africa (RSA, 1996)The provision of an adequate and sustainable waste service delivery system in the Municipal jurisdiction has had many challenges and there has been a very little progress with regard to significant movement in this area. Constitution of the Republic of South Africa places the responsibility on government to ensure that every person has access to basic services, in order to make sure that poor people or households are not discriminated against due to their economic status. The National Environmental Management Waste Act (59 of 2008) compels municipalities to put in place Integrated Waste Management Plans (IWMPs) and provide receptables for recyclables. The National policy for the Provision of Basic Refuse Removal Services to indigent households also came into effect at a time when the Waste Act had been enacted.

| Solid Waste Service Delivery Levels |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Households |  |  |  |
| Description | 2009/10 | 2010/11 | 2011/12 | 2012/13 |  |  |
|  | Actual | Actual | Actual | Actual |  |  |
|  | No. | No. | No. | No. |  |  |
| Solid Waste Removal: (Minimum level) |  |  |  |  |  |  |
| Removed at least once a week | 11393 | 11393 | 23872 | 23872 |  |  |
| Minimum Service Level and Above sub-total |  |  |  |  |  |  |
| Minimum Service Level and Above percentage |  |  |  |  |  |  |
| Solid Waste Removal: (Below minimum level) |  |  |  |  |  |  |
| Removed less frequently than once a week | 11393 | 11393 | 11393 | 11393 |  |  |
| Using communal refuse dump | 551 | 551 | 551 | 551 |  |  |
| Using own refuse dump | 6532 | 6532 | 6532 | 6532 |  |  |
| Other rubbish disposal | N/A | N/A | N/A | N/A |  |  |
| No rubbish disposal | 2229 | 2229 | 2229 | 2229 |  |  |
| Below Minimum Service Level sub-total |  |  |  |  |  |  |
| Below Minimum Service Level percentage |  |  |  |  |  |  |
| Total number of households |  |  | 31586 | 31586 |  |  |
| Households - Solid Waste Service Delivery Levels below the minimum |  |  |  |  |  |  |
|  |  |  |  |  | Households |  |
| Description | 2009/2010 | 2010/11 | 2011/12 | 2012/13 |  |  |
|  | Actual | Actual | Actual | Original Budget | Adjusted Budget | Actual |
|  | No. | No. | No. | No. | No. | No. |
| Formal Settlements |  |  |  |  |  |  |
| Total households |  | 23871 | 23872 | 23.872 | 23.872 | 0 |
| Households below minimum service level |  |  |  |  |  |  |
| Proportion of households below minimum service level |  | 2371 | 23872 | 23.872 | 23.872 | 0 |
| Informal Settlements |  | 8 | 8 |  |  |  |
| Total households |  |  |  |  |  |  |
| Households ts below minimum service level |  |  |  |  |  |  |
| Proportion of households ts below minimum service level |  | 23871 | 23872 | 23.872 | 23.872 | 0 |

| Waste Management Service Policy Objectives Taken From IDP |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Service Objectives | Outline Service Targets | 2010/11 |  | 2011/12 |  | 2012/13 |  |  |  |
|  |  | Target | Actual | Target | Actual | Target |  | Actual |  |
| Service Indicators |  |  |  |  |  |  |  |  |  |
| (i) | (ii) |  |  |  |  |  |  |  |  |
| Service Objective :To coordinate and monitor infrastructure development for provision and access to basic services |  |  |  |  |  |  |  |  |  |
| eg. Provision of weekly collection service per household (HH) | Proportionate reduction in average weekly collection failures year on year (average number of collection failures each week) | 23872 | 23872 | 23872 | 23872 | 23872 |  | 23872 |  |
| Future capacity of existing and earmarked (approved use and in council possession) waste disposal sites | The amount of spare capacity available in terms of the number of years capacity available at the current rate of landfill usage | 5.5HA | 5.5HA | 5.5HA | 5.5HA | 6.5 HA |  | 6.5HA |  |
| Proportion of waste that is recycled | Volumes of waste recycled as a percentage of total volume of waste disposed of at landfill sites. | N/A | N/A | N/A | N/A | N/A |  | N/A |  |
| Proportion of landfill sites in compliance with the Enviromental Conservation Act 1989. | x% of landfill sites by volume that are being managed in compliance with the Enviromental Conservation Act 1989. | 100% | 100% | 100% | 100% |  | 100% |  | 100% |

| Employees: Solid Waste Management Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 2 | 2 | 0 | 0% |
| 4 - 6 | 9 | 9 | 9 | 0 | 0% |
| 7 - 9 | 1 | 1 | 1 | 0 | 0% |
| 10 - 12 | 2 | 2 | 2 | 0 | 0% |
| 13 - 15 | 13 | 13 | 13 | 0 | 0% |
| Total | 27 | 27 | 27 | 0 |  |
| Employees: Waste Disposal and Other Services |  |  |  |  |  |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 2 | 2 | 0 | 0% |
| 4 - 6 | 9 | 9 | 9 | 0 | 0% |
| 7 - 9 | 1 | 1 | 1 | 0 | 0% |
| 10 - 12 | 2 | 2 | 2 | 0 | 0% |
| 13 - 15 | 13 | 13 | 13 | 0 | 0% |
| Total | 27 | 27 | 27 | 0 | 0% |
| Financial Performance 212/13: Solid Waste Management Services |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 7 502 779.05 | 12 619 000 | 895 4 000 | 8 954 000 |  |
| Expenditure: |  |  |  |  |  |
| Employees | 3 555 307.95 | 5 218 477.38 | 4 695 820.26 | 3 555 307.95 |  |
| Repairs and Maintenance |  |  |  |  |  |
| Other |  |  |  |  |  |
| Total Operational Expenditure | 73 43 830 01 | 96 97 000 | 96 99 000 | 96 99 000 |  |
| Net Operational (Service) Expenditure | 73 43 830 01 | 96 97 000 | 96 99 000 | 96 99 000 |  |

3.4     ELECTRICITY

INTRODUCTION TO ELECTRICITY

The Municipality has electricity distribution licences issued by NERSA in terms of the Electricity Act 41 of 1987.The license covers the following areas for distribution:

- Grater Northam RLC

- Thabazimbi TLC(Whole)

- Warmbad-Pienaarsrivier RLC(Portion)

- Rooiberg

Currently the Municipality is Electricity Service provider in Thabazimbi town,Regorogile extensions 3,5,6,7,9 Rooiberg and Raphuti

Note: Recent legislation includes the Electricity Amendment Acts 1989; 1994; 1995; and the Electricity Regulation Act 2006.

CHALLENGES ON ELECTRICITY

- Illegal connection

- Limited number of vending stations

- Lack of finance for rinfencing process

- The use of retention money for funding other activities

| Electricity Service Delivery Levels |  |  |  |
| --- | --- | --- | --- |
| Households |  |  |  |
| Description | 2010/11 | 2011/12 | 2012/13 |
|  | Actual | Actual | Actual |
|  | No. | No. | No. |
| Energy: (above minimum level) |  |  |  |
| Electricity (at least min.service level) | 9679 | 9679 | 11393 |
| Electricity - prepaid (min.service level) | 9821 | 9821 | 11560 |
| Minimum Service Level and Above sub-total | 19500 | 19500 | 22953 |
| Minimum Service Level and Above Percentage |  |  |  |
| Energy: (below minimum level) |  |  |  |
| Electricity (< min.service level) |  |  |  |
| Electricity - prepaid (< min. service level) |  |  |  |
| Other energy sources | 780 | 780 | 918 |
| Below Minimum Service Level sub-total | 780 | 780 | 918 |
| Below Minimum Service Level Percentage |  |  |  |
| Total number of households | 20280 | 20280 | 23871 |

| Households - Electricity Service Delivery Levels below the minimum |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Households |  |
| Description | 2010/11 |  | 2011/12 | 2012/13 |  |  |  |
|  | Actual |  | Actual | Original Budget | Adjusted Budget |  | Actual |
|  | No. |  | No. | No. | No. |  | No. |
| Formal Settlements |  |  |  |  |  |  |  |
| Total households | 23871 23871 |  | 23871 | 23.872 | 23.872 |  | 0 |
| Households below minimum service level |  |  |  |  |  |  |  |
| Proportion of households below minimum service level |  |  | 23871 | 23.872 | 23.872 |  | 0 |
| Informal Settlements | 8 |  | 8 |  |  |  |  |
| Total households |  |  |  |  |  |  |  |
| Households below minimum service level |  |  |  |  |  |  |  |
| Proportion of households below minimum service level | 23871 |  | 23871 | 23.872 | 23.872 |  | 0 |

| Electricity Service Policy Objectives Taken From IDP |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Service Objectives | Outline Service Targets | 2010/11 |  | 2011/12 |  | 2012/13 |  |
|  |  | Target | Actual | Target | Actual | Target | Actual |
| Service Indicators |  |  |  |  |  |  |  |
| (i) | (ii) |  |  |  |  |  |  |
| Service Objective :To coordinate and monitor infrastructure development for provision and access to basic services |  |  |  |  |  |  |  |
| eg. Provision of minimum supply of electricity | Additional households (HHs) provided with minimum supply during the year (Number of HHs below minimum supply level) | 758 | 620 | 156 | 100 | 0 | 0 |

| Employees: Electricity Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 2 | 2 | 0 | 0% |
| 4-6 | 6 | 12 | 8 | 0 | 0% |
| 7 - 9 | 1 | 4 | 2 | 0 | 0% |
| 10 - 12 | 5 | 6 | 5 | 0 | 0% |
| 13 - 15 | 1 | 1 | 1 | 0 | 0% |
| 16 - 18 | 8 | 8 | 8 | 0 | 0% |
| 19 - 20 |  |  |  | 0 | 0% |
| Total | 21 | 33 | 26 | 0 | 0% |
| Financial Performance 2012/13: Electricity Services |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 51 556 561 | 49 928 000 | 49 926 925 | 49 926 925 |  |
| Expenditure: |  |  |  |  |  |
| Employees | 4 190 495.23 | 4 942 179.81 | 2 700 339.69 | 4 190 495.23 |  |
| Repairs and Maintenance | 6 421 000 | 1 454 000 | 1 454 000 | 1 454 000 |  |
| Other |  |  |  |  |  |
| Total Operational Expenditure | 39 842 518.7 | 26 917 000 | 45 692 433.86 | 45 692 433.86 |  |
| Net Operational (Service) Expenditure | 39 842 518.7 | 26 917 000 | 45 692 433.86 | 45 692 433.86 |  |
| Capital Expenditure 2012/13: Electricity Services |  |  |  |  |  |
| Capital Projects | 2012/13 |  |  |  |  |
|  | Budget | Adjustment Budget | Actual Expenditure | Variance from original budget | Total Project Value |
| Total All | 4 700 000 | 4 700 000 | 4 700 000 | 0 |  |

COMMENT ON ELECTRICITY SERVICES PERFORMANCE OVERALL:

The municipality provide both the formal settlement and the informal settlement with electricity. With the increase of the new households of informal settlement, has a negative impact on the reduction of the backlog is at a decreasing rate(every financial year for the electricity priority list of the number of new households are counted The municipality is negotiating with Eskom and NERSA for the takeover of electricity distribution in Northam

HOUSING

| Percentage of households with access to basic housing |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Year end | Total households (including in formal and informal settlements) | Households in formal settlements | Percentage of HHs in formal settlements | Households in informal settlements | Percentage of HHs in informal settlements |
| 2010/11 | 31485 | 23771 | 75% | 7714 | 25% |
| 2011/12 | 31585 | 23871 | 76% | 7714 | 24% |
| 2012/13 | 31585 | 23871 | 76% | 7714 | 24% |

| Housing Service Policy Objectives Taken From IDP |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Service Objectives | Outline Service Targets | 2010/11 |  | 2011/12 |  | 2012/13 |  |
|  |  | Target | Actual | Target | Actual | Target | Actual |
| Service Indicators |  |  |  |  |  |  |  |
| (i) | (ii) |  |  |  |  |  |  |
| Service Objective : To coordinate and monitor infrastructure development for provision and access to basic services |  |  |  |  |  |  |  |
| eg. Provision for housing for all households | Number of Additional houses provided during the year (Houses required at year end) | 150 | 100 | 1 | 100 | 150 | 100 |

| Employees: Housing Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 1 | 1 | 1 | 1 | 0% |
| 4 – 6 |  |  |  |  |  |
| 7 – 9 | 1 | 1 | 1 | 1 | 0% |
| Total | 2 | 2 | 2 | 2 | 0% |

CHAPTER 4

FREE BASIC SERVICES AND INDIGENT SUPPORT

| Free Basic Services To Low Income Households |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Number of households. |
|  | Total | Households earning less than R1,100 per month |  |  |  |  |  |  |  |  |
|  |  |  | Free Basic Water |  | Free Basic Sanitation |  | Free Basic Electricity |  | Free Basic Refuse |  |
|  |  | Total | Access | % | Access | % | Access | % | Access | % |
| 2010/11 |  |  | 2579 |  | 2579 |  | 719 |  | 2579 |  |
| 2011/12 |  |  |  |  |  |  |  |  |  |  |
| 2012/13 |  |  | 221 |  | 221 |  |  |  | 221 |  |

| Free Basic Service Policy Objectives Taken From IDP |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Service Objectives | Outline Service Targets | 2010/11 |  | 2011/12 |  | 2012/13 |  |
|  |  | Target | Actual | Target | Actual | Target | Actual |
| Service Indicators |  |  |  |  |  |  |  |
| To coordinate and monitor infrastructure development for provision of access to basic services |  |  |  |  |  |  |  |
| Number of jobs created through EPWP projects |  |  |  |  |  |  |  |
| To create jobs through EPWP projects | Number of job opportunities created | 442 | 224 | 189 | 255 | 189 | 255 |

COMMENT ON FREE BASIC SERVICES AND INDIGENT SUPPORT:

The implementation of a policy of providing free basic services to poor and indigent communities is a complex task that will require a co-ordinated effort from national, provincial and local spheres of government. A number of challenges and constraints that will face municipalities relate to their technical and institutional readiness, the socio-political conditions that are prevalent in their area, and their financial positions. Some (mostly metropolitan) municipalities will find it relatively easy to implement the policy while others will find it extremely difficult and challenging. The strategies that they embark upon will have to take cognisance of these constraints and of the means to overcome them.

PROTECTION SERVICES

| Employees: Road Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 2 | 2 | 2 | 0% |
| 4 - 6 | 2 | 2 | 2 | 2 | 0% |
| 7 - 9 | 4 | 4 | 4 | 4 | 0% |
| 10 - 12 | 2 | 2 | 2 | 2 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| Total | 10 | 10 | 10 | 10 | 0% |
| Financial Performance 2012/13: Road Services |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 34 750 000 | 42 153 000 | 42 153 000 | 42 153 000 |  |
| Expenditure: |  |  |  |  |  |
| Employees | 10 752 122.08 | 14 642 751.84 | 14 502 539.45 | 10 752 122.08 |  |
| Repairs and Maintenance | 1 838 000 | 8 010 000 | 8 010 000 | 8 010 000 |  |
| Other |  |  |  |  |  |
| Total Operational Expenditure | 21 597 000 | 29 354 000 | 30 603 904.97 | 30 603 904.97 |  |
| Net Operational (Service) Expenditure | 21 597 000 | 29 354 000 | 30 603 904.97 | 30 603 904.97 |  |
| Capital Expenditure 2012/13: Road Services |  |  |  |  |  |
| Capital Projects | 2012/13 |  |  |  |  |
|  | Budget | Adjustment Budget | Actual Expenditure | Variance from original budget | Total Project Value |
| Total All | 2 300 000 | 2 300 000 | 2 300 000 |  |  |

DEVELOPMENT OF MUNICIPAL ROADS

| Development of municipal roads as required | xxx kms of municipal roads developed |
| --- | --- |
| 2009/10 | 2.421KM |
| 2010/11 | 8.696KM |
| 2011/12 | 3.574KM |

COMMENT ON THE PERFORMANCE OF ROADS OVERALL:

The municipality has powers and functions on internal roads in Thabazimbi ,Northam, Rooiberg and Leeuwpoort The municipality during the financial year 12/13 aimed to improve accessibility of services to the communities with the aim of upgrading arterial roads. The implementation of paving of roads at Regorogile Ext 5 reduced the number of unemployed youth

| Employees: Storm water Services |  |  |  |  |
| --- | --- | --- | --- | --- |
| Job Level | 2012/13 |  |  |  |
|  | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | % |
| 0 – 3 | 2 | 2 | 2 | 0% |
| 4 – 6 | 1 | 1 | 1 | 0% |
| 7 – 9 | 1 | 1 | 1 | 0% |
| 10 – 12 | 4 | 4 | 4 | 0% |
| 13 – 15 | 16 | 16 | 16 | 0% |
| 16 – 18 | 0 | 0 | 0 | 0% |
| Total | 24 | 24 | 24 | 0% |

COMPONENT C: PLANNING AND DEVELOPMENT

This component provides the initiatives facilitated by the Department of Planning and Economic Development The main sections to be addressed are the Town Planning and Local Economic Development.  This component is kick-started by highlighting the challenges and opportunities, followed by the overall performance of the Town Planning, and then the Local Economic Development

INTRODUCTION TO PLANNING

Thabazimbi Municipality is living up to its mission of ‘promoting, implementing and ensuring the financially and environmentally sustainable and development of the Municipality with a diversified and viable economy that provided an environment and services that benefit all.’ Town Planning division should ensure security of tenure to all by 2014, availability of land for development, coordinated and harmonious human settlements, as well as to ensure informed spatial decision making for municipal towns. All the town planning and building activities within the municipal area are governed and regulated by the Town Planning Scheme, Ordinances, National Building Regulation, as well as the Spatial Development Framework and Land Use Management System.

| Applications for Land Use Development |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Detail | Formalization of Townships |  | Rezoning |  | Built Environment |  |
|  | 2007/08 | 2008/2009 | 2009/10 | 2010/11 | 2011/12 | 2012/13 |
| Planning application received |  |  |  | 4 | 19 | 32 |
| Determination made in year of receipt |  |  |  | 0 | 27 | 28 |
| Determination made in following year |  |  |  | 4 | 27 | 0 |
| Applications withdrawn |  |  |  | 0 | 0 | 0 |
| Applications outstanding at year end |  |  |  | 4 | 27 | 4 |

| Service Objectives | Outline Service Targets | 2011/12 |  | 2012/13 |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Target | Actual | Target | Actual |
| Service Indicators |  | *Previous Year |  | *Previous Year |  |
| (i) | (ii) |  |  |  |  |
| Determine planning application within a reasonable timescale | Approval or rejection of all build environment applications within a x weeks | Determination within x weeks | Determination within x weeks | Determination within 12 weeks | Determination within 12 weeks |
|  | Reduction in planning decisions overturned | X planning decisions overturned | X planning decisions overturned | 5% planning decisions overturned | 5% planning decisions overturned |
|  |  | 0 | 0 | 0 | 0 |

| Employees: Planning Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 4 | 4 | 4 | 4 | 0% |
| 4 – 6 | 3 | 3 | 3 | 3 | 0% |
| 7 – 9 | 3 | 3 | 3 | 3 | 0% |
| 10 – 12 | 0 | 0 | 0 | 0 | 0 |
| 13 – 15 | 2 | 2 | 2 | 2 | 0% |
| 16 – 18 | 0 | 0 | 0 | 0 | 0% |
| 19 – 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 12 | 12 | 12 | 12 |  |
| Financial Performance 2012/13: Planning Services |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 704 000 | 1 496 000 | 1 495 000 | 1 495 000 |  |
| Expenditure: |  |  |  |  |  |
| Employees | 4 162 852.14 | 5 128 663.74 | 4 504 900.36 | 4 162 852.14 |  |
| Repairs and Maintenance |  |  |  |  |  |
| Other | 1 235 147.86 | 1 264 336.26 | 1 887 099.64 | 2 769 147.86 |  |
| Total Operational Expenditure | 5 398 000 | 6 393 000 | 6 392 000 | 6 392 000 |  |
| Net Operational (Service) Expenditure | 21 597 000 | 29 354 000 | 30 603 904.97 | 30 603 904.97 |  |

INTRODUCTION TO COMMUNITY AND SOCIAL SERVICES

This is to promote the wellbeing of the community at large

| Employees: Library |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 1 | 1 | 1 | 1 | 0% |
| 4 – 6 | 1 | 1 | 1 | 1 | 0% |
| 7 – 9 | 0 | 0 | 0 | 0 | 0% |
| 10 – 12 | 1 | 1 | 1 | 1 | 0% |
| 13 – 15 | 0 | 0 | 0 | 0 | 0% |
| 16 – 18 | 0 | 0 | 0 | 0 | 0% |
| 19 – 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 3 | 3 | 3 | 3 | 0% |
| Financial Performance 2012/13: Parks, sports, recreation |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) |  | 1 000 |  |  |  |
| Expenditure: |  |  |  |  |  |
| Employees | 2 955 633.36 | 3 554 769.77 | 3 287 542.55 | 2 955 633.36 |  |
| Repairs and Maintenance |  |  |  |  |  |
| Other | 776 226.21 | 1 049 230.23 | 1 868 316.91 | 2 200 226.10 |  |
| Total Operational Expenditure | 3 731 859.57 | 4 604 000 | 5 155 859 46 | 5 155 859 46 |  |
| Net Operational (Service) Expenditure | 3 731 859.57 | 4 604 000 | 5 155 859 46 | 5 155 859 46 |  |
| Capital Expenditure 2012/13: Library |  |  |  |  |  |
| Capital Projects | 2012/13 |  |  |  |  |
|  | Budget | Adjustment Budget | Actual Expenditure | Variance from original budget | Total Project Value |
| Total All | 1 000 000 | 1 000 000 | 1 000 000 | 1 000 000 |  |

CEMETERIES AND CREMATORIUMS

INTRODUCTION TO CEMETORIES

Cemeteries are promoting the wellbeing of the community at all times

| Employees: Cemeteries |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 | 2012/13 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 2 | 2 | 0 | 0% |
| 4 - 6 | 0 | 0 | 0 | 0 | 0% |
| 7 - 9 | 0 | 0 | 0 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 2 | 2 | 2 | 2 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 4 | 4 | 4 | 4 |  |
| Financial Performance 2012/13: Cemeteries |  |  |  |  |  |
| Details | 2011/12 | 2012/13 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 164 749 96 | 258 000 | 258 000 | 258 000 |  |
| Expenditure: |  |  |  |  |  |
| Employees | 247 842.90 | 346 425.11 | 298 690.86 | 247 842.90 |  |
| Repairs and Maintenance | 543 000 | 341 000 | 341 000 | 341 000 |  |
| Other |  |  |  |  |  |
| Total Operational Expenditure | 315 840.93 | 693 000 | 2 566 000 | 2 566 000 |  |
| Net Operational (Service) Expenditure | 315 840.93 | 693 000 | 2 566 000 | 2 566 000 |  |

MUNICIPAL INFRASTRUCTURE GRANT EXPENDITURE

| Municipal Infrastructure Grant (MIG)* Expenditure 2012/13 on Service backlogs |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Details | Budget | Adjust- ment Budget | Actual | Variance |  | Major conditions applied by donor (continue below if necessary) |
|  |  |  |  | Budget | Adjustment Budget |  |
| Infrastructure - Road transport |  |  |  |  |  |  |
| Roads, Pavements & Bridges | 42 153 000 | 42 153 000 | 42 153 000 |  |  |  |
| Total | 42 153 000 | 42 153 000 | 42 153 000 |  |  |  |

COMMENT ON LOCAL JOB OPPORTUNITIES:

Lot of jobs has been implemented through the project of EPWP by paving the internal streets at Regorogile and even cleaning of all 12 wards. More than 814 jobs created from 2009-2014 financial years

| Jobs Created during 2012/13 by LED Initiatives (Excluding EPWP projects) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Total Jobs created / Top 3 initiatives | Jobs created | Jobs lost/displaced by other initiatives | Net total jobs created in year | Method of validating jobs created/lost |
|  | No. | No. | No. |  |
| Total (all initiatives) |  |  |  |  |
| Initiative A (12/13) | 177 |  | 860 | 2 permanent and 175 temporary |
| Initiative B (11/12) |  |  |  |  |
| Initiative C (11/12) |  |  |  |  |
| Job creation through EPWP* projects |  |  |  |  |
| Year | EPWP Projects | Jobs created through EPWP projects |  |  |
|  | No. | No. |  |  |
| 10/11 | Paving of internal streets | 224 |  |  |
| 11/12 | Paving of internal streets | 259 |  |  |
| 12/13 | Paving of internal streets | 224 |  |  |

| Local Economic Development Policy Objectives Taken From IDP |  |  |  |
| --- | --- | --- | --- |
| Service Objectives | Outline Service Targets | 2011/12 | 2012/13 |
|  |  | Target |  |
| Service Indicators |  | *Current Year | Following Year |
| (i) | (ii) |  |  |
| Service Objective :To reduce illiteracy |  |  |  |
| eg. Training of people in essential skills: x, y, z | Number of people trained (including retrained upskilled) | x people trained | x people to be trained |
|  |  | 60 | 5 |

| Employees: Local Economic Development Services |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 |  |  |  |  |  |  |  |
|  | Posts | Employees |  |  | Vacancies (fulltime equivalents) |  | Vacancies (as a % of total posts) |  |
|  | No. | No. |  |  | No. |  | % |  |
| 0 - 3 | 2 | 2 |  |  | 2 |  | 0% |  |
| 7 - 9 | 1 | 1 |  |  | 1 |  | 0% |  |
| Total | 3 | 3 |  |  | 3 |  | 0% |  |
| Financial Performance 2012/13: Local Economic Development Services |  |  |  |  |  |  |  |  |
| Details | 2012/13 |  |  |  |  |  |  |  |
|  | Original Budget | Adjustment Budget |  |  | Actual |  | Variance to Budget |  |
| Total Operational Revenue (excluding tarrifs) | 64 000 | 17 000 |  |  | 17 000 |  |  |  |
| Expenditure: |  |  |  |  |  |  |  |  |
| Employees | 757 372.80 | 736 256.48 |  |  | 565 434.72 |  |  |  |
| Repairs and Maintenance |  |  |  |  |  |  |  |  |
| Other | 631 627.20 |  |  |  | 167 565.30 |  |  |  |
| Total Operational Expenditure | 1 389 000 | 733 000 |  |  | 733 000 |  |  |  |
| Net Operational (Service) Expenditure | 1 389 000 | 733 000 |  |  | 733 000 |  |  |  |
| Variances are calculated by dividing the difference between the Actual and Original Budget by the Actual. |  |  |  |  |  |  |  |  |

CHAPTER 5- ORGANIZATIONAL DEVELOPMENT PERFORMANCE

5. 1 HUMAN RESOURCE SERVICES

INTRODUCTION TO HUMAN RESOURCE SERVICES

– Special attempt was made to fill critical vacant positions that affect service delivery.  Personnel budget was increased to make provision for a reviewed Organizational Structure and placements as a measure to address more efficient services during the year

SERVICE STATISTICS FOR HUMAN RESOURCE SERVICES

| Human Resource Services Policy Objectives Taken From IDP |  |  |  |
| --- | --- | --- | --- |
| Service Objectives | Outline Service Targets | 2012/13 |  |
| Service Indicators |  | *Current Year | Following year |
| Service Objective: To attract, develop and retain best human capital |  |  |  |

| Employees: Human Resource Services |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Job Level | 2011/12 |  |  |  |  |  |  |  |
|  | Posts |  | Employees |  | Vacancies (fulltime equivalents) |  | Vacancies (as a % of total posts) |  |
|  | No. |  | No. |  | No. |  | % |  |
| 0 – 3 | 2 |  | 2 |  | 2 |  | 0% |  |
| 4 – 6 |  |  |  |  |  |  |  |  |
| 7 – 9 | 1 |  | 1 |  | 1 |  | 1 |  |
| Total | 3 |  | 3 |  | 3 |  | 1 |  |
| Financial Performance 2012/13: Human Resource Services |  |  |  |  |  |  |  |  |
| Details | 2012/13 |  |  |  |  |  |  |  |
|  | Original Budget |  | Adjustment Budget |  | Actual |  | Variance to Budget |  |
| Total Operational Revenue (excluding tarrifs) | 1 800 000 |  | 1 800 000 |  | 1 800 000 |  |  |  |
| Expenditure: |  |  |  |  |  |  |  |  |
| Employees | 3 449 431.48 |  | 3 302 410.10 |  | 5 099 912.35 |  |  |  |
| Repairs and Maintenance |  |  |  |  |  |  |  |  |
| Other | 2 594 568.52 |  | 2 741 589.90 |  | 944 087.65 |  |  |  |
| Total Operational Expenditure | 6 044 000 |  | 6 044 000 |  | 6 044 000 |  |  |  |
| Net Operational (Service) Expenditure | 6 044 000 |  | 6 044 000 |  | 6 044 000 |  |  |  |

5.2 INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

INTRODUCTION TO INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

VPNC (Virtual Private Network Connection) Refers to Network access outside the Municipality building/offices and  to provide support to users in order to deliver services to community.

VPN – (Virtual Private Network) upgrade – refers to Network access outside the office of the Municipality to connect 3 satellite offices (Northam, Rooiberg and Leeupoort) in order to do support for services to be delivered  to community.

Upgrade of Prepaid Electricity system (Cash Power) – It was upgraded in order to sell prepaid electricity easily to community of Regorogile and Rooiberg.

Financial System The Financial System was changed from PROMIS to MUNSOFT in order for Community to pay accounts easily without any hassle.

| Employees: ICT Services |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Job Level | 2012/13 |  |  |  |  |  |  |  |
|  | Posts |  | Employees |  | Vacancies (fulltime equivalents) |  | Vacancies (as a % of total posts) |  |
|  | No. |  | No. |  | No. |  | % |  |
| 0 – 3 | 2 |  | 1 |  | 2 |  | 2 |  |
| 4 – 6 | 1 |  | 1 |  | 1 |  | 0% |  |
| 7 – 9 | 1 |  | 1 |  | 1 |  | 0% |  |
| Total | 4 |  | 3 |  | 4 |  | 2 |  |
| Financial Performance 2012/13: ICT Services and council support |  |  |  |  |  |  |  |  |
| Details | 2012/13 |  |  |  |  |  |  |  |
|  | Original Budget |  | Adjustment Budget |  | Actual |  | Variance to Budget |  |
| Total Operational Revenue (excluding tarrifs) |  |  | 215 000 |  | 215 000 |  |  |  |
| Expenditure: |  |  |  |  |  |  |  |  |
| Employees | 3 261 823.25 |  | 2 625 256.35 |  | 2 671 642.94 |  |  |  |
| Repairs and Maintenance |  |  |  |  |  |  |  |  |
| Other |  |  | 5 592 743.65 |  | 5 546 357.06 |  |  |  |
| Total Operational Expenditure | 3 182 000 |  | 8 218 000 |  | 8 218 000 |  |  |  |
| Net Operational (Service) Expenditure | 3 182 000 |  | 8 218 000 |  | 8 218 000 |  |  |  |
| Variances are calculated by dividing the difference between the Actual and Original Budget by the Actual. |  |  |  |  |  |  |  |  |
| Capital Expenditure 2012/13: ICT Services |  |  |  |  |  |  |  |  |
| Capital Projects | 2012/13 |  |  |  |  |  |  |  |
|  | Budget | Adjustment Budget |  | Actual Expenditure |  | Variance from original budget |  | Total Project Value |
| Total All | 1 720 000 | 1 720 000 |  | 1 720 000 |  |  |  |  |

COMMENT ON THE PERFORMANCE OF ICT SERVICES OVERALL:

We achieved the upgrading of our Financial System (Munsoft), Prepaid Electrical System (Cash Power), VPN & VPNC.

Challenges- Wireless connectivity devices are burned when there is lighting.

Solution- Upgrade wireless infrastructure to be protected

| Details | 2012/13 |  |  |  |
| --- | --- | --- | --- | --- |
|  | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue (excluding tarrifs) | 422 000 | 422 000 | 422 000 |  |
| Expenditure: |  |  |  |  |
| Employees | 853 616.13 | 833 690.77 | 468 561.97 |  |
| Repairs and Maintenance |  |  |  |  |
| Other | 4 425 383.87 |  |  |  |
| Total Operational Expenditure | 5 279 000 | 336 000 | 366 000 |  |
| Net Operational (Service) Expenditure | 5 279 000 | 336 000 | 366 000 |  |

COMPONENT J: ORGANISATIONAL PERFOMANCE SCORECARD

This component includes:  Annual Performance Scorecard Report for the current year.

FINANCE

|  | KPA | Strategic Objective |  | Programme / Focus area | Performance Indicators | Baseline Actual 2011-12 | Annual Target 2012-2013 | Q1 | Q2 | Q3 | Q4 | Actual achievement | Evidence | Variance | Remedial action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Financial Viability | Enhance financial viability and accountability |  | Budget | Timeous submission of annual financial statements to office of the AG | 31 August | 31 August 2012 | 1 | - | - | - | 1 | AFS | 0 | None |
|  |  | Enhance financial viability and accountability |  | Budget | Number of management sessions held | 4 | 7 | - | - | 2 | 2 | 4 | Minutes | 0 |  |
|  |  | Enhance financial viability and accountability |  | Budget | Timeous submission of sec71&72 MFMA reports | 12 | 12 | 3 | 6 | 9 | 12 | 12 | Sec71&72 report | 0 | 0 |
|  |  | Enhance financial viability and accountability |  | Budget | Budget compiled in terms of MFMA and budget regulations | Compliance with chapter 4 of MFMA | Budget tabled by 31 March 2013 and to be adopted by the 31 May 2013 | - | - | 1 | - | 1 | Council minutes | 0 | 0 |
|  |  | Enhance financial viability and accountability | Budget |  | 12 Monthly bank reconciliation done in 2011/12 | 12 Monthly bank reconciliation | 12 | 3 | 6 | 9 | 12 | 12 | Copies | 0 | 0 |
|  | Financial viability | Enhance financial viability and accountability |  | Compile and updated investment register | 2011/12 investment register | Updated 2012/13 investment register compiled | - | - | - | - | 1 | 1 | Updated investment register | 0 | 0 |
|  |  | Enhance financial viability and accountability |  | Grant register | # of Grant register update | 4 | 4 | 1 | 2 | 3 | 4 | 4 | Signed grand registers | 0 | 0 |
|  |  | Enhance financial viability and accountability |  | Assets management | # of GRAP asset register updates | 12 | 12 | 3 | 6 | 9 | 12 | 12 | Updated asset register | 0 | 0 |

Corporate services

|  |  | KPA | Strategic Objective | Programme / Focus area | Performance Indicators | Baseline Actual 2011-12 | Annual Target 2012-2013 | Q1 | Q2 | Q3 | Q4 | Actual achievement | Evidence | Variance | Remedial action |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Municipal good governance & public participation | Develop and implement integrated management and governance system | Administration, council support and legal services | Number of management sessions held | 9 | 11 | 4 | 6 | 8 | 10 | 12 | Minutes | 0 | N/A |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | # EC/MC & sub-committee minutes completed | 16 | 16 | 3 | 6 | 9 | 12 | 9 | Minutes | 0 | Meetings to be held every month |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | % of resolutions updated for EC& MC | 100% | 100% | 70% | 80% | 90% | 100% | 90% | Minutes | 0 | Implementation of resolutions by managers |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | # of properties successfully transferred | 100% | 100% | - | - | - | - | - | 0 | 0 | Land needed |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | # of cases pending | 100% | 100% | - | - | 4 | 4 | 0 | No judgement | 0 | N/A |  |  |  |  |
|  |  | Municipal good governance& public participation | Develop and implement integrated management and governance system | Administration, council support and legal services | # management meeting recorded | 12 | 12 | 4 | 6 | 8 | 10 | 12 | Minutes | 0 | N/A |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | # of by-laws to passed by council | 4 | 4 | 1 | 2 | 3 | 4 | 4 | publication | 0 | N/A |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | Organisational structure reviewed | 1 | 1 | 1 | - | - | - | 1 | Council resolution | 0 | N/A |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | % of positions filled |  | 80% |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | # of meetings in terms of occupational health & safety | 4 | 4 | 1 | 2 | 3 | 4 | 4 | Minuets | 0 | N/A |  |  |  |  |
|  |  | Municipal good governance &public participation | Develop and implement integrated management and governance system | Administration, council support and legal services | Submission of WSP | 1 | 1 | - | - | - | 1 | 1 | Report | 0 | N/A |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | % of annual training for employees | 43.59% | 85.2% | 1 | 2 | 3 | 4 | 4 | Report | 0 | N/A |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | # of meeting for LLF | 3 | 4 | 1 | 2 | 3 | 4 | 4 | Minuets | 0 | N/A |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | # of performance reviews /assessments | 2 | 2 | 1 | 2 | 3 | 4 | 4 | P.O.E | 0 | Quarterly assessments |  |  |  |  |
|  |  | Municipal public participation& good governance | Develop and implement integrated management and governance system | Administration, council support and legal services | 100%Cascading of OPMS to Middle management | 0 | 100% | - | - | - | - | 0 | None | 0 | Workshop and cascading to all levels |  |  |  |  |
|  |  |  | Develop and implement integrated management and governance system | Administration, council support and legal services | % of network related challenges reported | 100% | 100% | 25% | 50% | 75% | 80% | 80% | Reports | 0 | To change the current network infrastructure |  |  |  |  |
| Social & community services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | KPA | Strategic Objective | Programme / Focus area | Performance Indicators | Baseline Actual 2011-12 | Annual Target 2012-2013 | Q1 | Q2 | Q3 | Q4 | Actual achievement | Evidence | Variance | Remedial action |  |  |  |  |
|  |  | Basic service delivery | Promote the well-being of all communities | Protection services | % of cases pending | 0% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  | Basic service delivery | Promote the well-being of all communities | Protection services | # of service provider paid on time | 0% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | % of compliance to SABS code for road wealthy | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | % of compliance with K53 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | % of learners tested | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | %of Drivers tested | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | % vehicles tested | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | % of licensing processed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # of days taken from notification of documents | 5 | 5 | 1 | 2 | 3 | 4 | 5 | Report | 0 | 0 |  |  |  |  |
|  |  | Basic service delivery | Promote the well-being of all communities | Protection services | % of cash collected daily | 100% | 100% | 25% | 50% | 75% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # written fines issued |  | 1200 | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # of special operations |  | 15 | 100% | 100% | 100% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # of petrol vehicles procured | 6 | 6 | - | - | - | - | 0 | N/A | 0 | More budget must be provided |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # of parks maintained |  | 8 | 2 | 4 | 6 | 8 | 8 | Report | 0 | More budget must be provided |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | Feasibility study on land & cemetery | 2 | 3 | - | - | - | - | 0 | 0 | 0 | Lack of land |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # reports on graves provided | 12 | 12 | 1 | 2 | 3 | 4 | 0 | Report | 0 | 0 |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # sports filled maintained | 4 | 4 | 1 | 2 | 3 | 4 | 4 | N/A |  | None |  |  |  |  |
|  |  | Basic service delivery | Promote the well-being of all communities | Protection services | # of community halls cleaned | 3 | 3 | 1 | 2 | 3 | 4 | 3 | Roaster | 0 | None |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | % of refuse collected | 100% | 100% | 25% | 50% | 75% | 100% | 100% | Report | 0 | None |  |  |  |  |
|  |  |  | Promote the well-being of all communities | Protection services | # of campaigned held | 4 | 4 | 1 | 2 | 3 | 4 | 4 | Report | - | None |  |  |  |  |
| Planning & economic development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | KPA | Strategic Objective | Programme / Focus area | Performance Indicators | Baseline Actual 2011-12 | Annual Target 2012-2013 | Q1 | Q2 | Q3 | Q4 | Actual achievement | Evidence | Variance | Remedial action |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | # management sessions to address AG issues | 100% | 100% | 25% | 50% | 75% | 100% | 100% | Report | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | # cases pending | 100% | 100% | - | - | - | - | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  | L E D | Ensure economic growth | P E D | # meetings to promote tourism | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Minuets | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | # of Consultative meetings | 4 | 4 | 1 | 2 | 3 | 4 | 4 | Minuets | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | % of SMMEs supported | - | 50% | - | 4 | 4 | 4 | - | Attendance register | - | - |  |  |  |  |
|  |  | L E D | Ensure economic growth | P E D | # of new jobs created by private sector | - | 4 | 1 | 2 | 3 | 4 | 4 | Report | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | # of new jobs created by public sector | 4306 | 4 | 1 | 2 | 3 | 4 | 4 | Report | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | # corporative established | 24 | 25 | 5 | 5 | 5 | 10 | 25 | Report | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | # of sites inspected | - | 200 | 50 | 50 | 50 | 50 | 200 | Report | None | N/A |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | % of applications processed ( Municipal or planned land ) | 80% | 80% | 80% | 80% | 80% | 80% | 80% | Reports | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | % of processed applications in town establishment to council | 80% | 80% | 80% | 80% | 80% | 80% | 80% | Reports | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | % of processing of applications for subdivisions | 80% | 80% | 80% | 80% | 80% | 80% | 80% | Reports | 0 | 0 |  |  |  |  |
|  |  |  | Ensure economic growth | P E D | % of applications of closure of parks | 80% | 80% | 80% | 80% | 80% | 80% | 80% | Reports | 0 | 0 |  |  |  |  |
| Technical services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Ensure economic growth | P E D |
|  | BASIC SERVICES |  | Develop audit action plan | MTS | # of management sessions to address AG queries | 100% | 100% | 25% | 50% | 75% | 100% | 100% | Report | 0 |  | 0 |  |  |  |
|  |  |  | Implement EPWP | MTS | % of EPWP funds utilised | 0 | 100% | 100% | 100% | 100% | 100% | 100% | Report | 0 |  | 0 |  |  |  |
|  |  |  | Management of discipline and grievance | MTS | # of cases pending | 0% | 100% | 1 | - | - | - | 0 | No judgement | 0 |  | 0 |  |  |  |
|  |  |  | Project management | MTS | % of completed MIG projects | - | 100% | 25% | 50% | 75% | 100% | 100% | Report | 0 |  | 0 |  |  |  |
|  |  |  | TBZ upgrading of WWTW | MTS | R-value spent on upgrading | 0 | R16M | R4M | R8M | R12M | R16M | R16M | Report | 0 |  | 0 |  |  |  |
|  |  |  | 5Ml/d waste water treatment | MTS | R-value spent | 0 | R24.4M | R6.1m | R12.2m | R18.2m | R24.4M | R24.4M | Report | 0 |  |  |  |  |  |
|  |  |  | Maintain sewer network | MTS | R-value spent | 0 | R225737 | R56434 | R112875 | R169302 | R225737 | R225737 | Report | 0 |  | 0 |  |  |  |
|  |  |  | New master plan | MTS | R-value spent | 0 | R330750 | N/A | R1653750 | R330750 | N/A | R330750 | Report | 0 |  | 0 |  |  |  |

OFFICE OF MUNICIPAL MANAGER

|  | KPA | Strategic Objective |  | Programme / Focus area | Performance Indicators | Baseline Actual 2011-12 | Annual Target 2012-2013 | Q1 | Q2 | Q3 | Q4 | Actual achievement | Evidence | Variance | Remedial action |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Good Governance | Internal audit |  | COO | Number of risk based audits conducted | 5 | 6 | 1 | 2 | 3 | 4 | 4 | Minuets | 0 |  |
|  |  | Public participation |  | COO | Number of ward committee members trained | 120 | 120 | 38 | - | - | - | 38 | Report | 38 | Training must be given |
|  |  | Communications |  | COO | Number of reviewed communication strategy | 1 | 1 | 1 | - | - | - | 1 | Report | 0 | None |
|  |  | IDP |  | COO | Implemented IDP strategic session | 1 | 1 | 1 | - | - | - | 1 | Minuets | 0 | 0 |
|  |  | PMS | COO |  | Approved SDBIP | 1 | 1 | 1 | - | - | - | 1 | Approved SDBIP | 0 | 0 |

COMPONENT B: MANAGING THE MUNICIPAL WORKFORCE

| Employees |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description | 2010/11 | 2011/12 |  |  |  |
|  | Employees | Approved Posts | Employees | Varience | Varience |
|  | No. | No. | No. | No. | % |
| Water | 27 | 27 | 27 |  |  |
| Waste Water (Sanitation) |  |  |  |  |  |
| Electricity | 21 | 21 | 21 |  |  |
| Waste Management |  |  |  |  |  |
| Housing |  |  |  |  |  |
| Waste Water (Stormwater Drainage) |  |  |  |  |  |
| Roads |  |  |  |  |  |
| Transport | 0 | 0 | 0 |  |  |
| Planning | 12 | 12 | 12 |  |  |
| Local Economic Development | 3 | 3 | 3 |  |  |
| Totals | 90 | 90 | 90 |  |  |
| For waste water and roads are the same people who are executing the job. |  |  |  |  |  |

| Vacancy Rate 2011/12 |  |  |  |
| --- | --- | --- | --- |
| Designations | *Total Approved Posts | *Variances (Total time that vacancies exist using fulltime equivalents) | *Variances (as a proportion of total posts in each category) |
|  | No. | No. | % |
| Municipal Manager | 1 | N/A | 0% |
| CFO | 1 |  |  |
| Other S57 Managers (excluding Finance Posts) | 5 | 5 | 0% |
| Other S57 Managers (Finance posts) |  |  |  |
| Municipal Police | N/a | N/a | N/a |
| Fire fighters | Two |  |  |
| Senior management: Levels 13-15 (excluding Finance Posts) |  |  |  |
| Total |  |  |  |
| Note: *For posts which are established and funded in the approved budget or adjustments budget (where changes in employee provision have been made). Full-time equivalents are calculated by taking the total number of working days lost (excluding weekends and public holidays) while a post remains vacant and adding together all such days lost by all posts within the same set (e.g. ‘senior management’) then dividing that total by 250 to give the number of posts equivalent to the accumulated days. |  |  |  |
| Turn-over Rate |  |  |  |
| Details | Total Appointments as of beginning of Financial Year | Terminations during the Financial Year | Turn-over Rate* |
|  | No. | No. |  |
| 2011/12 | 22 | 20 | 0 |
| * Divide the number of employees who have left the organisation within a year, by total number of employees who occupied posts at the beginning of the year |  |  |  |

Comment on vacancies and turnover

We have   filled all senior positions that is section 56&57 managers we are in the process of restructuring our organogram as well as finalising the placement process.

5.6 POLICIES

| HR Policies and Plans |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Name of Policy | Completed | Reviewed | Date adopted by council or comment on failure to adopt |
|  |  | % | % |  |
| 1 | Affirmative Action |  |  |  |
| 2 | Attraction and Retention |  |  |  |
| 3 | Code of Conduct for employees |  |  |  |
| 4 | Delegations, Authorisation & Responsibility |  |  |  |
| 5 | Disciplinary Code and Procedures |  |  | 03 September 2010 |
| 6 | Essential Services |  |  |  |
| 7 | Employee Assistance / Wellness |  |  |  |
| 8 | Employment Equity |  |  | 09 October 2012 |
| 9 | Exit Management |  |  |  |
| 10 | Grievance Procedures |  |  |  |
| 11 | HIV/Aids |  |  |  |
| 12 | Human Resource and Development |  |  |  |
| 13 | Information Technology |  |  |  |
| 14 | Job Evaluation |  |  |  |
| 15 | Leave |  |  |  |
| 16 | Occupational Health and Safety |  |  |  |
| 17 | Official Housing |  |  |  |
| 18 | Official Journeys |  |  |  |
| 19 | Official transport to attend Funerals |  |  |  |
| 20 | Official Working Hours and Overtime |  |  |  |
| 21 | Organisational Rights |  |  |  |
| 22 | Payroll Deductions |  |  |  |
| 23 | Performance Management and Development |  |  |  |
| 24 | Recruitment, Selection and Appointments |  |  |  |
| 25 | Remuneration Scales and Allowances |  |  |  |
| 26 | Resettlement |  |  |  |
| 27 | Sexual Harassment |  |  |  |
| 28 | Skills Development |  |  |  |
| 29 | Smoking |  |  |  |
| 30 | Special Skills |  |  |  |
| 31 | Work Organisation |  |  |  |
| 32 | Uniforms and Protective Clothing |  |  |  |
| 33 | Other: |  |  |  |
| Use name of local policies if different from above and at any other HR policies not listed. |  |  |  |  |

Summary of AG Findings

| Directorate | Number of findings | Number of resolved findings (YTD) | Number of unresolved findings (YTD) |
| --- | --- | --- | --- |
| Finance | 25 | 18 | 7 |
| Technical services | 5 | 3 | 2 |
| MM’s Office | 23 | 10 | 13 |
| P.E.D | - | - | - |
| Corporate services | 2 | 2 | - |
| Community Services | - | - | - |
| TOTAL | 55 | 33 | 22 |